Eni S.p.A. – Procurement Function

Type of document: Upstream Standard Contract

Topic: M101EI Construction, Mechanical, Electro-instrumental Work - General conditions

Issue date: December 2013 (Rev.24)

Prepared and issued by: APR/PCOM-A2

___________________________________________________________________

TABLE OF CONTENTS

- DEFINITIONS AND INTERPRETATION

- TERMINATION WITH CAUSE

- TERMINATION WITHOUT CAUSE

- REGULATIONS FOR ORGANIZED CRIME PREVENTION

- TECHNICAL/MANAGEMENT DOCUMENTATION - INSPECTIONS/DOCUMENTS APPROVAL

- PRIORITY OF DOCUMENTS

- KNOWLEDGE OF THE AREA OF OPERATIONS – SITE INSPECTION

- AREA OF OPERATIONS AND/OR CONSTRUCTION SITE

- HANDLING AND CARRIAGE OF MATERIALS AND WORK

- CONTRACTOR'S EMPLOYEES AND EQUIPMENT

- CONTRACTOR'S MATERIALS

- COMPANY'S MATERIALS

- WORK SCHEDULE – TIME SCHEDULES

- GOODS IN PROCESS ACCOUNT/DELIVERY OF THE WORK TO THIRD PARTIES/GOODS HELD IN STORE

- VESSELS

- CUSTOMS FORMALITIES

- DELIVERY OF THE AREA FOR THE COMMENCEMENT OF THE WORK

- INSPECTIONS – TESTS

- GOOD PRESERVATION OF THE WORK PERFORMED

- TESTING AND TAKING RECEIPT OF COMPLETED WORK

- START-UP TESTS – RUNNING SIMULATIONS

- CHANGES

- PARTIES' REPRESENTATIVES

- WORKS REGISTER AND LOG-BOOK

- CONTRACTOR'S OBLIGATIONS

- COMPANY’S OBLIGATIONS

- HEALTH, SAFETY AND ENVIRONMENT

- RADIATION SOURCES

- CONTRACTOR'S REQUIREMENTS

- PARTIES' LIABILITIES

- INSURANCE

- SUSPENSION - DISCONTINUANCE OF THE WORK

- PENALTIES

- ACCOUNTING DOCUMENTS - ACCOUNTING AND RESERVATIONS

- WORK ON A TIME AND MATERIALS BASIS

- SUPPLIES ON A REIMBURSABLE BASIS

- NEW PRICES AND/OR RATES

- FIXED PRICES AND/OR RATES

- WORK PROGRESS REPORT

- PAYMENTS

- PAYMENT MODALITIES AND INVOICING

- NON-ASSIGNMENT OF CREDITS

- GUARANTEES

- AUDIT

- TAXES AND DUTIES

- INSOLVENCY PROCEDURES

- ASSIGNMENT OF THE CONTRACT

- SUBCONTRACTING   Alternative A

- SUBCONTRACTING   Alternative B

- COMPLIANCE WITH THE REGULATIONS ON INSURANCE, CONTRIBUTIONS AND CONTRACTS

- INTELLECTUAL PROPERTY AND PATENT RIGHT

- FORCE MAJEURE

- COMPETENT JURISDICTION   Alternative A

- DISPUTES – COMPETENT JURISDICTION   Alternative B

- GOVERNING LAW

- AMENDMENTS TO THE CONTRACT

- CONFIDENTIAL INFORMATION, ADMINISTRATIVE RESPONSIBILITY AND PRIVACY

- NOTICES

- DEFINITIONS AND INTERPRETATION

Except as otherwise provided for in the CONTRACT, the terms and expressions herein below will have the following meaning:

  - Definitions

    - CONTRACTOR shall mean the Company which has been indicated as such in the Letter of Award.

    - AREA OF OPERATIONS AND/OR CONSTRUCTION SITE shall mean the area where CONTRACTOR performs the WORK under the CONTRACT, as specified in the Special Conditions.

    - CONSTRUCTION SITE AREA: shall mean the area within the CONSTRUCTION SITE where CONTRACTOR arranges its equipment, means and personnel for the performance of the WORK.

    - EQUIPMENT shall mean the infrastructure, means, equipment, appliances, machines, motor vehicles provided by CONTRACTOR for the performance of the WORK.

    - COMPANY'S CENTRES shall mean all those places designated by COMPANY for the storage of its materials and equipment.

    - COMPANY shall mean the Company designated as such in the Letter of Award and in particular, with regard to the aspects related to environment, health, safety, quality and public safety, shall mean the person who has the role of Company on the basis of the HSE delegation/empowerment system.

    - CONTRACT shall mean the agreement concluded between the PARTIES for the execution of the WORK. The CONTRACT conditions are set out in the set of contractual documents indicated in the Letter of Award.

    - END DATE OF THE WORK shall mean the date of COMPANY’s taking receipt of the WORK, certified by the “End date of the work report”.

    - COMMENCEMENT DATE OF THE WORK shall mean the date of effective commencement of the WORK, certified by the “Commencement date of the work report".

    - WORK shall mean all the service and/or work and/or processing and/or products, elements, components which CONTRACTOR shall perform and/or carry out and/or implement under the CONTRACT and which shall be completed and tested successfully.

    - MATERIALS shall mean all equipment, ferrous and/or non-ferrous pieces, hardware, equipment and appliances in general, required for the performance of the WORK, excluding the WORK under paragraph 1.1.3.

    - PARTY shall mean either COMPANY or CONTRACTOR, according to the context;

PARTIES shall mean COMPANY and CONTRACTOR jointly.

    - CONTRACTOR’S REPRESENTATIVE shall mean the person authorized by CONTRACTOR to act on its behalf and that COMPANY may consult at any time during the performance of the CONTRACT.

    - COMPANY’S REPRESENTATIVE shall mean the person duly authorized by COMPANY to act on its behalf and that CONTRACTOR may consult at any time during the performance of the CONTRACT.

    - CONTRACT ADMINISTRATOR shall mean the Unit specified in the Letter of Award and duly represented whose main tasks are: the management of the relations with CONTRACTOR, the verification of compliance with the schedules and times set out in the CONTRACT, the technical-operational control of the WORK and subsequent technical acceptance thereof.

    - SUBCONTRACTOR shall mean any contractor (whether an individual or a corporation) engaged by CONTRACTOR for the performance of any part of the WORK.

    - TECHNICAL DOCUMENTATION (drawings – Technical Specification - standards –  Bills  of quantities, Contract Specifications and Price List set forth in the Special Conditions): it illustrates the characteristics related to the performance of the WORK, it indicates the extent and nature of  the WORK, it describes the technical-management modalities, it provides information on the type and quantity of MATERIALS needed, as well as other essential data on the nature and scope of the WORK, the amount of costs and charges that such WORK involves, and precise indications on the results that COMPANY prescribes and expects.

    - AFFILIATE shall mean in respect of a PARTY:

      - any company or other legal entity which is controlled by a PARTY, or

      - any company or legal entity which directly or indirectly controls a PARTY, or

      - any company or other legal entity which is directly or indirectly controlled by any company or legal entity which directly or indirectly controls a PARTY.

For the purpose of this definition, a company or legal entity is considered “controlled” by another company or legal entity when the latter owns directly or indirectly the majority of votes which can be exercised at an ordinary meeting, or is entitled to appoint more than half the directors, of the former.

1.1.19. 	HUMAN RIGHTS shall mean the inalienable rights of all individuals, without any distinction, by virtue of belonging to humankind. They are based on the recognition of the inherent dignity, freedom and equality of all human beings. HUMAN RIGHTS have been sanctioned by the United Nations in the Universal Declaration of Human Rights (10 December 1948) as the “foundation of freedom, justice and peace in the world”.

HUMAN RIGHTS fall into two main categories:

- civil and political rights: include, inter alia, the right to life and physical integrity, the right to freedom of thought and expression, the right to take part in the government of one’s own country, the right not to be arrested without due cause, the right to an impartial trial, and the right to own property;

- economic, social and cultural rights: include, inter alia, the right to employment, fair and satisfactory working conditions, equal pay for equal work, health and education.

Furthermore, in more recent times, so-called “third generation rights” are gradually making headway. They include the right to self-determination, peace, development and environmental protection.

1.1.20.	THIRD PARTIES shall mean any individual or corporation other than the PARTIES.

1.1.21    SUBCONTRATTO shall mean a contract covering activities other than those that are part of the CONTRACT, carried out in the AREA OF OPERATIONS:

    - if, individually in an amount greater than 2% (two per cent) of the amount of the activities assigned or, in any case, in an amount greater than Euro 100,000, but only if the incidence of the cost of manpower and personnel is lower than 50% (fifty per cent) of the amount of the contract to be awarded;

    - if individually in an amount lower than 2% (two per cent) of the amount of the activities assigned or, in any case, in an amount lower than Euro 100,000, regardless of the incidence of manpower and personnel.

Furthermore the following, because of their specificity and regardless of the place where the activities are carried out, their amount and the incidence of manpower, shall be considered "SUBCONTRATTO":

    - the assignment of specific activities to independent workers;

    - the sub-supply from catalogue of information technology products.

  - Interpretation

    - The use of singular terms and expressions does not exclude that they may be construed as plurals as well and vice versa, if the context so allows and this responds to the intention of the PARTIES.

    - Headings and sub-headings of each CONTRACT Article/clause are for ease of reference only and shall not be considered as part of the CONTRACT nor affect the construction or interpretation of the CONTRACT Articles/clauses.

    - Except as otherwise stated, the numbers and/or letters of the Articles and/or clauses and/or paragraphs cited in the General Conditions and/or Special Conditions refer respectively only to the Articles and/or clauses and/or paragraphs of said General Conditions and/or Special Conditions.

- TERMINATION WITH CAUSE

  - Express termination clause

Except as provided for in Art. “Confidential Information, Administrative Responsibility and Privacy”, as well as those on termination and/or term in other provisions of the CONTRACT and the regulations in force, COMPANY will be entitled to terminate the CONTRACT, under art. 1456 of the Italian Civil Code, if:

______________________________________________________________________

(Nota: nel caso di Contratti di valore superiore ai 1.500 Euro,  sostituire la clausola 2.1 con la formulazione di seguito riportata)

Subject to the provisions set out in Art. “Confidential Information, Administrative Responsibility and Privacy”, as well as those on termination and/or term in other provisions of the CONTRACT and the regulations in force, including the cause of termination as required by art. 3 of Law no. 136 of 2010 as amended, COMPANY will be entitled to terminate the CONTRACT, under art. 1456 of the Italian Civil Code, if:

______________________________________________________________________

    - CONTRACTOR does not commence the WORK within the date set out in the Special Conditions or if it does not complete it, for reasons ascribable thereto, by the agreed times, and possibly subject to penalties, set out in the relevant Article provided for in the CONTRACT;

    - CONTRACTOR does not submit to COMPANY the deliverables within the times under the CONTRACT;

    - CONTRACTOR does not perform the WORK in compliance with the conditions set out in the CONTRACT and in particular if it uses employees and/or EQUIPMENT not meeting the agreed requirements, or if it does not arrange for the prompt replacement of the malfunctioning EQUIPMENT, or any part thereof;

    - CONTRACTOR subcontracts any part of the WORK without prior authorization in writing by COMPANY or if it assigns the CONTRACT to THIRD PARTIES;

    - CONTRACTOR and/or SUBCONTRACTOR do/does not comply with the provisions of Art. "Health, Safety and Environment", or do/does not comply with the measures required by the “Consolidated Document concerning interference-related risk assessment” (“Documento Unico di Valutazione dei Rischi da Interferenze”) (DUVRI), or the Safety and Co-ordination Plan (PSC) and/or its own Operational Safety Plan (POS) or the Coordinated Health and Safety Document (DSSC);

    - CONTRACTOR makes, without authorization in writing by COMPANY, changes and/or variations to the WORK and/or the related performance scheme and does not restore them to the same conditions as set out in the CONTRACT;

    - CONTRACTOR fails to comply with the current rules on insurance, salary, taxes, contributions and social security of its employees and the provisions on accident prevention;

    - CONTRACTOR fails to maintain the insurance policies provided for in the CONTRACT or if it fails to extend them;

    - CONTRACTOR becomes defaulting to its creditors or shall transfer its goods to creditors;

    - CONTRACTOR discontinues the performance of the WORK in case of disputes;

    - CONTRACTOR breaches the confidentiality agreement on the information received pursuant to the CONTRACT;

    - the certifications submitted or produced by CONTRACTOR, for the purpose of award of the CONTRACT or its performance, are, at any time, irregular;

    - CONTRACTOR no longer meets the requirements indicated in Art. "Contractor’s requirements";

    - CONTRACTOR does not comply with any of its obligations related to the regulations for organized crime prevention.

  - For CONTRACT termination in compliance with this Article COMPANY will send to CONTRACTOR proper notice in writing.

  - In the cases set out in clause 2.1, COMPANY may also enforce the procedure provided for in art. 1454 of the Italian Civil Code, by instructing CONTRACTOR in writing to remedy the disputed facts within the time that COMPANY will deem fit, and in any case no less than 15 (fifteen) days from notice receipt. Once said period has gone by in vain, the CONTRACT shall be deemed terminated and COMPANY will be entitled to compensation for damages, which CONTRACTOR shall pay within 60 (sixty) days from receipt of the relevant debit note.

  - If CONTRACT termination takes place after commencement of the performance of the WORK, CONTRACTOR shall deliver to COMPANY the WORK performed after receipt of the written notice set forth in clause 2.2 above.

Before taking receipt of the WORK, a report of ascertainment shall be drawn up and signed by the PARTIES.

The amount of the above-mentioned WORK shall be calculated on the basis of the prices and/or rates under the CONTRACT and notably in compliance with the Special Conditions. Such amount shall be entered into the report of ascertainment.

If CONTRACTOR refuses to sign the report of ascertainment, COMPANY may request a Notary or an expert and two witnesses, alien to the WORK, to draw it up (Sworn expert’s report).

  - COMPANY is also entitled to terminate the CONTRACT if CONTRACTOR is subject to any of the insolvency procedures provided for in Art. “Insolvency Procedures”, if the Force Majeure event set out in Art. “Force Majeure” continues for over 30 (thirty) days, and if CONTRACTOR no longer meets the requirements necessary for the qualification process.

- TERMINATION WITHOUT CAUSE

  - Termination without cause by COMPANY

    - Except as provided for in Art. “Confidential Information, Administrative Responsibility and Privacy”, COMPANY may, at its own discretion and without giving any justification to CONTRACTOR, by delivering prior written notice, terminate the CONTRACT without cause in whole or in part or request total or partial discontinuance of the WORK, at any time.

Only the WORK which on COMPANY’s notice date will be already completed will not suffer from the effects of termination without cause or discontinuance.

Termination without cause or discontinuance will be effective as of the date of receipt by CONTRACTOR of COMPANY’s relevant notice.

3.1.2.	If termination without cause takes place before CONTRACTOR has commenced the CONSTRUCTION SITE organization, COMPANY's decision shall not result in CONTRACTOR having any right to compensation for damages, nor to any payment for failure to perform the WORK.

3.1.3.	If termination without cause takes place during the CONSTRUCTION SITE organization or in any case before the actual commencement of the WORK, CONTRACTOR shall have the right to receive only an indemnification, whose amount shall be agreed jointly by the PARTIES in relation to out-of-pocket expenses and documented costs incurred by CONTRACTOR for transportation and set-up of the CONSTRUCTION SITE and relevant EQUIPMENT.

3.1.4.	If termination without cause takes place during the performance of the WORK, COMPANY shall pay CONTRACTOR as follows:

      - the amount corresponding to the value of the WORK performed until the date of termination without cause, provided that the WORK was performed in a workmanlike manner and in compliance with the provisions contained in the CONTRACT. The amount shall be determined on the basis of the prices and/or rates established by the CONTRACT.

      - the amount corresponding to the value of the MATERIALS already present at the CONSTRUCTION SITE or already ordered and for which it was not possible to cancel the relevant purchase orders.

The WORK performed by CONTRACTOR and the supplies carried out by CONTRACTOR, paid by COMPANY as stated above, shall become COMPANY's property "as is".

  - Termination without cause by CONTRACTOR

Given the importance attached to the WORK by COMPANY, for no reason whatsoever, not even for disputes before a court, may CONTRACTOR terminate the CONTRACT without cause or discontinue in whole or in part the performance of the WORK.

4. REGULATIONS FOR ORGANIZED CRIME PREVENTION (if applicable)

4.1.	The validity of the CONTRACT is conditional upon the possession and preservation by CONTRACTOR of the requirements set out by the regulations in force for organized crime prevention.

To this end CONTRACTOR undertakes to promptly notify COMPANY of any changes in the CONTRACTOR’s/SUBCONTRACTOR’s corporate organization or of their Directors, occurred during performance of the CONTRACT, and submit copy of the documents evidencing the changes of the subjects involved in the verifications related to organized crime prevention.

4.2.	In case of failure to meet or loss of the above-mentioned requirements by CONTRACTOR or any SUBCONTRACTORS, COMPANY shall have the right to terminate the CONTRACT or to declare it terminated under and for the purposes of art. 1456 of the Italian Civil Code.

4.3.	In case of loss of the above-mentioned requirements by any SUBCONTRACTORS, CONTRACTOR undertakes to immediately replace them with other SUBCONTRACTORS subject to prior authorization thereof by COMPANY.

If CONTRACTOR fails to comply with such obligation of replacement, COMPANY shall have the right to terminate the CONTRACT under the above-mentioned art. 1456 of the Italian Civil Code.

- TECHNICAL/MANAGEMENT DOCUMENTATION - INSPECTIONS/DOCUMENTS APPROVAL

  - The technical documentation (drawings - specifications – standards – bills of quantities etc.) established by the CONTRACT illustrates the characteristics related to the performance of the WORK, it indicates the extent and nature of the WORK, it describes the technical-operating modalities, it provides information on the type and quantity of MATERIALS needed, as well as other essential data on the nature and scope of the WORK, the amount of costs and charges that such WORK involves, and precise indications on the results that COMPANY prescribes and expects.

The technical documentation shall therefore be deemed prescriptive and binding, but it shall be developed by CONTRACTOR for construction purposes.

  - CONTRACTOR shall perform the WORK in compliance with the description contained in the CONTRACT technical/management documentation, without making any changes to the concept or any variants to the WORK extent  and characteristics; on the contrary, it shall review every aspect of the chapters of the documentation, arranging at its expense for the deletion of any inconsistencies, subject to prior notice to COMPANY, for any necessary additions, the performance of deliverables and drawings, the formulation of details, quality control, issue of any other elements required to perform and complete the WORK and deliver them to COMPANY completed and successfully tested.

Therefore, it shall be CONTRACTOR's responsibility to identify, in the light of COMPANY's technical/management documentation and of the documentation that it will prepare following its formulations, all the WORK that it shall perform, all the MATERIALS that it shall purchase, all the liabilities that it shall assume and all the expenses that it shall incur.

  - All the above-mentioned activities and, as a consequence, all the obligations and expenses that those activities impose on CONTRACTOR to complete the technical/management documentation and the WORK, are deemed identified and accepted by CONTRACTOR without any reservation whatsoever and may not result in special and extra payments, since the relevant cost is included in the prices and/or rates set forth in the CONTRACT.

For this purpose it is worth mentioning that any CONTRACTOR’s requests for reimbursement for any activities, purchases, hires etc., justified by an inaccurate and/or incomplete assessment of the above-mentioned activities, obligations and expenses, shall be rejected as lacking any contractual justification.

  - CONTRACTOR, after having carefully reviewed all the technical/management documentation supplied by COMPANY, including lists of MATERIALS, assumes all liabilities for the suitability and accurateness of said documentation.

If provided for, drawings, calculations, reports, deliverables and all other CONTRACTOR's deliverables shall become effective only when approved by COMPANY.

  - If, in COMPANY's opinion, CONTRACTOR's drawings, calculations and reports are insufficient or inadequate, COMPANY shall have the right to request CONTRACTOR to fully or partly revise them. CONTRACTOR shall be entitled to no additional payment or extension(s) of time.

  - The submission of deliverables to COMPANY shall take place within times that are consistent with the WORK schedule and in accordance with the prescriptions contained in the Management Specification.

Any delays attributable to CONTRACTOR in the submission of the deliverables affecting COMPANY's schedules may result in the immediate termination of the CONTRACT in compliance with Art. “Termination with Cause”.

  - Once revised by COMPANY, the deliverables prepared by CONTRACTOR shall form an integral part of the CONTRACT and for no reason may they be arbitrarily changed by CONTRACTOR.

  - The examination of deliverables by COMPANY will not imply that  COMPANY assumes any liability, which shall rest with CONTRACTOR.

  - All technical/management documentation, including deliverables that CONTRACTOR shall supply to COMPANY, shall be signed by people meeting the requirements established by applicable legislation.

  - All technical/management documentation shall meet the requirements set forth in the Management Specification.

CONTRACTOR shall deliver to COMPANY all technical documentation and constructive drawings updated as-built, within the times established by the Management Specification.

  - Any possible COMPANY’s comments shall be notified to CONTRACTOR within the times established by the Management Specification or within other times agreed between the PARTIES.

- PRIORITY OF DOCUMENTS

  - The documents which make up the CONTRACT form an integral part thereof and shall be construed systematically.

If a document has an ambiguous lexical meaning and/or is incomplete, clarifications and additions will be made through the other documents according to the following priority:

    - the Letter of Award;

    - the Special Conditions; the TECHNICAL SPECIFICATION; Appendix “E”- HSE-QR Requirements (Health, Safety, Environment, Quality and Radiation Protection Requirements); the DUVRI or PSC or DSSC; Appendix "A" -  Compensation and/or Appendix “B” - Price Schedule (if applicable);

    - the General Conditions;

    - the Drawings.

The above list of priorities will be used also in case of discrepancies among the documents or between individual clauses thereof.

  - The following is also understood between the PARTIES:

    - If the provisions contained in COMPANY’s technical/management documentation and deliverables and those contained in the Documents set out in the Commercial Section cited in the Letter of Award clash having regard to terms and conditions and not to technical aspects, the conditions provided for in the latter Documents shall prevail.

    - On the contrary, if the technical/management documentation and the deliverables contain any conditions in addition to the Documents set out in the Commercial Section cited in the Letter of Award, said conditions shall have full validity as if they were set forth in all contractual documents.

7.	KNOWLEDGE OF THE AREA OF OPERATIONS – SITE INSPECTION

7.1.	Indications as to the location of the AREA OF OPERATIONS were included in COMPANY’s  letter of Invitation to tender (RdO) or in the documentation attached thereto.

7.2.	Before formulating its tender, CONTRACTOR, if expressly requested by COMPANY, shall have carried out an inspection of the area where the WORK will be performed to satisfy itself as to the location of the AREA OF OPERATIONS, the conditions and circumstances  affecting the performance of the WORK and/or its outcome, the correctness and sufficiency of the rates and prices set forth in the CONTRACT.

7.3.	CONTRACTOR has confirmed in writing that it has carried out the inspection of the AREA OF OPERATIONS and represents that it assumes the risk of any difficulty occurring during the performance of the WORK, notwithstanding Art. 1664 – 2nd subsection of the Italian Civil Code.

8.	AREA OF OPERATIONS AND/OR CONSTRUCTION SITE

8.1.	For any WORK to be performed on COMPANY's areas, both onshore and offshore, the areas shall be delivered by COMPANY to CONTRACTOR ‘as is’.

Onshore areas, access and any right of way shall be procured by COMPANY at its expense.

8.2.	Delivery of the area shall take place by proper report signed by the Representatives of the PARTIES.

8.3.	As regards the area on which CONTRACTOR shall set up the CONSTRUCTION SITE, it may be supplied by COMPANY or it shall be found by CONTRACTOR at its expense, on the basis of the instructions supplied by COMPANY at the time of Invitation to Tender.

8.4.	The areas where CONTRACTOR's CONSTRUCTION SITE, if any, shall be located shall be appropriately arranged by CONTRACTOR at its expense; CONTRACTOR shall also equip the areas with sanitary-health equipment, water and energy connections (unless already existing), dumps and drainage, temporary shut-downs and any other requirements for the performance of the WORK, for employees' decency and for safety at the workplace.

8.5.	CONTRACTOR shall take special care in storing or stocking, within the AREA OF OPERATIONS, the materials supplied by COMPANY, it being understood that any damage, loss or theft shall be fully charged to CONTRACTOR.

8.6.	After delivery of the areas onshore any liability for guardianship, accident prevention, danger signalling, suitability of the temporary works, no entry signs etc., shall be charged to CONTRACTOR.

8.7.	For offshore activities, COMPANY shall make available to CONTRACTOR proper areas on its platforms and the possibility to accommodate CONTRACTOR's employees in COMPANY's relevant accommodation and/or other infrastructure.

8.8.	After completion of the WORK and within the date to be notified by COMPANY, CONTRACTOR shall clear the AREA OF OPERATIONS and restore it.

Any residual MATERIALS owned by COMPANY shall be carried by CONTRACTOR to COMPANY's CENTRE closest to the AREA OF OPERATIONS, or may be stored at the AREA OF OPERATIONS, according to COMPANY's requests.

Unless otherwise specified in the Special Conditions, all waste and waste materials resulting from the activities under the CONTRACT, whatever the place of origin thereof, shall be disposed of at authorized dumps at CONTRACTOR's expense, in accordance with the HSE-QR Requirements.

8.9.	To ensure the loading of the WORK for transport offshore it is essential that CONTRACTOR’s CONSTRUCTION SITE be equipped with a adequate berthing facilities and, that the seabed be appropriate for docking the vessels required by the CONTRACT.

No amount may be charged to COMPANY for the adjustment of the berthing facilities or for dredging said seabed should larger vessels with deeper draft than originally expected be used.

Likewise, COMPANY may not be charged with extra amounts for the strengthening and/or improvement of the CONSTRUCTION SITE and/or for the preparation and/or changes of slides (runaways) required for handling and loading the WORK on the vessel.

8.10.	COMPANY may request CONTRACTOR to store the WORK at the CONSTRUCTION SITE after the delivery date under the Special Conditions, both to complete it with ad-hoc installations by other Companies designated by COMPANY and for other reasons.

In that case, the PARTIES shall agree on a payment that CONTRACTOR shall receive for WORK storage and for allowing other Companies to access the CONSTRUCTION SITE.

8.11.	Historical, artistic, archaeological and paleontological objects found during the performance of the WORK, under art. 826 of the Italian Civil Code, lawfully belong to the State.

The finding of valuable items, not having the above-mentioned characteristics, shall be attributed according to the criteria set forth in art. 932 of the Italian Civil Code.

At the time of discovery, CONTRACTOR shall promptly inform COMPANY and the appropriate Authorities and shall adopt all adequate measures to prevent damage to or removal of the items.

If, for that purpose, suspension of the WORK is required, the relevant Italian laws and regulations shall apply .

9.	HANDLING AND CARRIAGE OF MATERIALS AND WORK

9.1.	If the MATERIALS to be transported, excluding radioactive sources, are delivered to CONTRACTOR at COMPANY's CENTRES, loading on CONTRACTOR's vehicles shall be carried out by COMPANY at its expense.

CONTRACTOR's radioactive sources may be delivered to COMPANY's CENTRES only in a proper area previously assigned by COMPANY and taken and managed by CONTRACTOR. CONTRACTOR expressly indemnifies and holds COMPANY harmless from and against any liability directly or indirectly connected with the activities carried out in that area.

The loading of MATERIALS in places where COMPANY does not have hoisting equipment or personnel available shall be carried out by CONTRACTOR at its expense.

The unloading of motor vehicles at the CONSTRUCTION SITE shall be carried out by CONTRACTOR at its expense.

9.2.	Land and sea transports shall be carried out by CONTRACTOR using approved vehicles and vessels, in perfect condition and under its full responsibility.

Air, sea and land transports of radioactive sources on national territory are exclusively carried out by Authorized Carriers under Decree passed by the appropriate Ministry as established by art. 5 of Law dated 31st December 1962, no. 1860, as amended from time to time (SEE NOTE 1). CONTRACTOR shall indemnify and hold COMPANY harmless from and against, and meet the cost of, any sanction inflicted by the Public Authorities on CONTRACTOR.

All MATERIALS shall be accompanied by the "Transport Document” (DdT).

9.3.	Loading the WORK and/or MATERIALS from CONTRACTOR's CONSTRUCTION SITE onto the vessel shall be carried out by CONTRACTOR.

The loading plan and procedure shall be for CONTRACTOR's account; CONTRACTOR shall obtain COMPANY's and/or the appropriate Certification Bodies' approval.

Any hoisting of the WORK on the vessel shall be carried out as required by the CONTRACT.

In that case, CONTRACTOR shall develop, at its expense, all detailed technical documents required for the performance of the hoisting activities, have them approved by COMPANY, by the Certification Body indicated by COMPANY and by the statutory Bodies.

A copy of the above-mentioned authorization shall be sent by CONTRACTOR to COMPANY before loading and hoisting.

Any adjustment and strengthening of the vessel shall be deemed an integral part of the hoisting and charged to CONTRACTOR.

9.4.	Onshore loading, carriage and unloading of CONTRACTOR's MATERIALS and EQUIPMENT used for offshore WORK shall always be performed by CONTRACTOR and the relevant costs shall be included in the prices and/or rates under the CONTRACT.

Hoisting of the above onto offshore platforms shall be carried out by cranes or winches installed therein or using other COMPANY's means and with the aid of CONTRACTOR's employees already present on the platform.

NOTE 1: The contract relating to carriage shall be between the Holder of the radioactive sources (who has the sources available on any account and holds the necessary authorizations or has filed the notification of practice) and the Authorized Carrier. CONTRACTOR, representing to be an Authorized Carrier, shall have the proper authorization Decree for the transport of sources, whether owned or THIRD PARTIES'.

10.	 CONTRACTOR'S EMPLOYEES AND EQUIPMENT

10.1.	Subject to the provisions of Appendix “E”- HSE-QR Requirements and the HSE Disciplinary Policy contained therein, CONTRACTOR undertakes to perform the WORK with employees who have the proper technical expertise and professional skills required for the WORK complexity, also in compliance with the current regulations on health, safety and environment.

Workers working with radioactive sources or X-ray machines or in any case in the presence of ionizing radiations, as directed by CONTRACTOR’s Qualified Expert, shall be classified for radiological risk, equipped, if so provided, with individual dosimeters and subjected to medical check-up and periodic medical examination by the Doctor in charge of medical examination.

If COMPANY believes that one or more CONTRACTOR’s employees do not possess the essential technical expertise for an effective performance of the WORK or behave so as to adversely affect the performance and/or the progress thereof due to carelessness, negligence, inefficiency or any other reasons related to people safety and security, COMPANY will notify and cause CONTRACTOR to adopt proper measures. For this purpose CONTRACTOR undertakes to take all the necessary actions, including replacement of employees at its expense, so as to ensure compliance with the contractual obligations.

CONTRACTOR will arrange, at its expense, for the immediate replacement of those people who are absent due to illness, injury, on holidays and on leave.

The replacement of CONTRACTOR’s employees shall not howsoever affect WORK continuity.

10.2.	CONTRACTOR shall ensure that its employees are provided with identification badges, complete with photograph, the worker's personal details and the name of CONTRACTOR. CONTRACTOR's employees are under the obligation to show the identification badges.

CONTRACTOR undertakes to ensure that employees of any SUBCONTRACTORS and/or any authorised Third Parties comply with this requirement.

10.3.	If required by applicable legislation, CONTRACTOR's employees shall be properly qualified by the appropriate Bodies (e.g. welding certificate, non-destructive testing certificate and certificate for storage/handling of radioactive sources).

10.4.	The EQUIPMENT shall be suitable in number, type and capacity for the type and quantity of the WORK assigned to CONTRACTOR and in any case proportional to the WORK schedule agreed between the PARTIES.

All EQUIPMENT shall be kept at the height of their efficiency by CONTRACTOR throughout the WORK duration. In case of faults or failures the EQUIPMENT which is not deemed at the height of their efficiency shall be promptly repaired or replaced by CONTRACTOR at its expense, and in any case in a manner and a time so as not to affect WORK continuity.

10.5.	All expenses for employees’ and EQUIPMENT's activities as well as those required to keep the EQUIPMENT efficient shall be included in the prices and/or rates under the CONTRACT.

EQUIPMENT efficiency shall be certified according to applicable legislation and Builders' instructions and the CONTRACT technical/management documentation.

10.6.	Any claims or remarks by COMPANY on the employees and EQUIPMENT shall be remedied by CONTRACTOR within the time set by COMPANY and to the full satisfaction thereof, under the penalty of discontinuance of the WORK.

11.	CONTRACTOR'S MATERIALS

11.1.	The type, characteristics and features of the MATERIALS to be used in the WORK, as well as the methods for testing and accepting the MATERIALS, are described in the CONTRACT.

Prior acceptance of the MATERIALS by COMPANY shall not constitute acceptance of the WORK where the MATERIALS were used.

CONTRACTOR shall remove from the CONSTRUCTION SITE those MATERIALS that are subject to wear and tear or in any case not compliant with the provisions contained in the CONTRACT.

11.2.	Any portion(s) of the WORK performed using MATERIALS, not up to the required standard in terms of type, characteristics and properties, , shall be rejected by COMPANY.

In addition, if it is ascertained that the MATERIALS used in the WORK are not first quality, CONTRACTOR shall demolish at its expense the part/s of the WORK not acceptable.

If, on the contrary, CONTRACTOR uses upon its initiative any MATERIALS of a higher quality, in terms of type, characteristics and properties, than as required by the CONTRACT and if those MATERIALS are accepted by COMPANY,  CONTRACTOR may not claim  any extra payments.

11.3.	All expenses relating to inspections, tests and checks of CONTRACTOR's MATERIALS shall be charged to CONTRACTOR.

COMPANY reserves the right to request additional tests on CONTRACTOR's MATERIALS; if those additional tests, to be taken at COMPANY's expense, show any non-acceptable defects or non-conformities, the relevant cost shall be charged to CONTRACTOR.

11.4.	Any delays in CONTRACTOR's MATERIALS availability and/or delays in the performance of the inspections, tests and checks thereof shall not entitle CONTRACTOR to request the extension of the END DATE OF THE WORK or of the deadlines established in the WORK progress schedule. CONTRACTOR shall keep at the CONSTRUCTION SITE quantities of MATERIALS to ensure normal WORK continuity with sufficient security margins.

11.5.	The documents that CONTRACTOR shall submit to COMPANY certifying the type of MATERIALS, inspections, tests and checks taken, their origin etc. are set forth in the CONTRACT. MATERIALS not certified by those documents shall not be accepted by COMPANY.

12.	COMPANY'S MATERIALS

12.1.	COMPANY may supply to CONTRACTOR a part of the MATERIALS to be used in the WORK with or without additional processing, according to the indications set forth in the CONTRACT.

12.2.	Upon taking receipt of COMPANY's MATERIALS, CONTRACTOR shall visually check their physical condition, notifying COMPANY of any deficiencies, damage or faults within 3 (three) days from the date of receipt thereof. Once said period has gone by, COMPANY's MATERIALS shall be deemed accepted by CONTRACTOR.

CONTRACTOR shall not be liable for any latent defects that cannot be noticed by visual check at the time of receipt of COMPANY's MATERIALS.

12.3.	All MATERIALS supplied by COMPANY shall be listed by CONTRACTOR in suitable registers of receipt. Those registers shall bear on the bottom of each sheet the signature of the Representatives of the PARTIES.

12.4.	Handling, storage, guardianship and good preservation of COMPANY's MATERIALS shall be CONTRACTOR's responsibility and the relevant cost shall be included in the prices and/or rates under the CONTRACT.

12.5.	Upon completion of the WORK, CONTRACTOR shall return all unused COMPANY's MATERIALS to the closest COMPANY's CENTRE; in case CONTRACTOR fails to return the MATERIALS, the corresponding value shall be charged to CONTRACTOR.

12.6.	Any delays in the delivery of COMPANY's MATERIALS to CONTRACTOR, not resulting in unavoidable stand-by times of all CONTRACTOR's staff or work suspension for periods longer than 90 (ninety) days, shall only give rise  to the extension of the END DATE OF THE WORK.

12.7.	CONTRACTOR shall process the MATERIALS supplied by COMPANY with technical diligence and cost-effectiveness. No waste in excess of the normal quantity nor deterioration of said MATERIALS greater than the unavoidable deterioration for the performance of the WORK shall be accepted.

Any loss of the MATERIALS, whatever the cause, including theft, as well as due to negligence attributable to CONTRACTOR, shall be charged to CONTRACTOR on the basis of COMPANY's supporting documents.

If the damage is recoverable under the Insurance effected by COMPANY where CONTRACTOR acts as co-insured, CONTRACTOR shall have the right to recover , in whole or in part, the cost relating to the amount charged by COMPANY.

13.	WORK SCHEDULE – TIME SCHEDULES

13.1.	The date by which the WORK shall be commenced and the date within which the WORK shall be delivered are set forth in the Special Conditions. The COMMENCEMENT DATE and END DATE OF THE WORK shall be confirmed and/or changed during the kick-off meeting the minutes of which shall form an integral part of the CONTRACT.

If the WORK can be divided into lots and the activities on each lot take place on different dates, the relevant “Report of commencement of the lot” and the relevant “Report of end of the lot” shall be drawn up separately  in respect of each lot.

13.2.	CONTRACTOR shall submit to COMPANY a WORK schedule (included between the commencement and end dates) drawn up and enclosed according to the modalities set forth in the Management Specification and notably said schedule shall be drawn up on a chart showing the progress of the main work groups and their respective date of completion and it shall indicate, in separate sheets, the staff (level and qualifications) and EQUIPMENT CONTRACTOR intends to use in order to meet the deadlines.

Once approved by COMPANY, the above-mentioned schedule shall become effective and CONTRACTOR shall fully meet the provisions contained therein. The approved schedule shall be binding upon CONTRACTOR, but it shall not bind COMPANY, who shall always have the right to demand changes thereof on the basis of its requirements.

If said schedule is not approved by COMPANY, COMPANY shall report its reservations to CONTRACTOR and shall establish, in agreement with CONTRACTOR, the date within which CONTRACTOR shall submit the schedule updated to COMPANY's satisfaction.

13.3.	The WORK is connected to other activities for which COMPANY has already assumed or might assume commitments with THIRD PARTIES. It is therefore implied that CONTRACTOR's failure to meet the time schedules may prove prejudicial to those commitments and result in economic damage to COMPANY.

CONTRACTOR shall therefore  meet the dates agreed and make up for lost time through its fault and/or cause within the times established by COMPANY and in any case adjust the composition of its staff and EQUIPMENT to specific needs; COMPANY shall not assume any expense or consequence resulting therefrom.

Non-compliance with these obligations shall be deemed a material breach and the relevant provisions contained in the CONTRACT shall apply; notably COMPANY may terminate the CONTRACT under Art. “Termination with Cause”.

It is worth mentioning that a 10% (ten percent) delay relative to the planned schedule shall be deemed material breach.

13.4.	The COMMENCEMENT DATE OF THE WORK and END DATE OF THE WORK, as well as the order of priority of the phases, due dates and other indications under the CONTRACT, may not be changed by CONTRACTOR except for the following reasons and upon written request in compliance with Art. "Changes":

13.4.1.	force majeure events (as set forth in Art. “Force Majeure”), ordinances by the authorities and legislative provisions;

13.4.2.	causes attributable to COMPANY.

For any extension(s) of the COMMENCEMENT DATE OF THE WORK and END DATE OF THE WORK the conditions cited in Art. “Delivery of the area for commencement of work” shall apply.

13.5.	Upon the occurrence of events, not attributable to CONTRACTOR, causing delays in the performance of the WORK, CONTRACTOR shall immediately notify COMPANY thereof in writing. The notice shall clearly state the reasons preventing CONTRACTOR from overcoming the events incurred, despite the adoption of measures suggested by its technical and organizational diligence.

In that case COMPANY shall have the right to grant an extension, on all or part of the WORK, as is fair based on the documentation submitted by CONTRACTOR.

COMPANY shall not take into consideration any circumstances due to planning or scheduling deficiencies by CONTRACTOR.

14.	GOODS IN PROCESSING ACCOUNT/DELIVERY OF THE WORK TO THIRD PARTIES/GOODS HELD IN STORE

14.1.	Goods in processing Account(Free issue Materials)

If CONTRACTOR receives from COMPANY any part of the materials to be incorporated in the WORK, with or without additional processing, COMPANY's provisions concerning the Goods in processing account are listed in the “ad hoc” attachment  (Facilities/District) cited in Exhibit “A”.

14.2.	Delivery of the WORK to THIRD PARTIES

If the WORK, or any part thereof, has to be delivered by CONTRACTOR to THIRD PARTIES, CONTRACTOR shall abide by COMPANY's provisions set forth in the attachment cited in Exhibit “B”.

14.3.	Goods held in store

If, due to operational requirements, COMPANY is unable to collect or receive the WORK, CONTRACTOR shall hold it in store until it is collected.

If this is the case, CONTRACTOR shall issue a "Declaration of storage of goods” drawn up in compliance with the specimen attached to Appendix “C”. Said declaration shall be registered with the Registry Office and officially dated by said Office.

The “Declaration of storage of goods” shall be sent to the address set forth in Art. “Goods held in store” of the Special Conditions.

COMPANY reserves the right to check that CONTRACTOR's registers listing the WORK held in store are properly kept, stamped and certified.

The WORK shall be stored at CONTRACTOR's facilities separately from CONTRACTOR's materials.

No areas other than those occupied by the  goods held in store shall be recognized.

Upon returning the WORK to COMPANY, CONTRACTOR shall:

14.3.1.	issue an invoice for the storage service if the service is not supplied to COMPANY free of charge. The invoice shall be marked "WORK stored at our facilities;

14.3.2.	issue a “Transport Document” (DdT) specifying:

      - reason: “return of COMPANY's GOODS held in store”;

      - references of COMPANY's delivery note/s (MAT7) at the time of storage.

15.	VESSELS

15.1.	The vessels that CONTRACTOR intends using for the WORK shall be accepted in writing by COMPANY. Acceptance will not constitute COMPANY's liability for the operation of the vessels and the outcome of the WORK.

Written acceptance of the above-mentioned vessels shall take place within the times provided for in the technical/management documentation of the CONTRACT or agreed between the PARTIES.

15.2.	As regards the above, the information that CONTRACTOR shall always provide to COMPANY, and for which it shall obtain COMPANY's approval, is listed herein below:

15.2.1.	Emergency vehicle to be permanently kept alongside the platform:

*	Self-propelled vehicle

*	Main dimensions

*	Power

*	Displacement

*	Speed

*	Logistic arrangements

*	Carrying capacity

*	Mooring equipment

*	R.I.N.A. seaworthiness certificate up to the limit inclusive of rig location being set up

*	Rescue equipment.

This vessel may  also be used as a logistic support vehicle, i.e. as a base for CONTRACTOR's crew accommodation on the platform concerned, if COMPANY cannot provide board and lodging on said platform.

*	Fast vehicle for shuttle service (shore- Platform) to be used for team shifts and for EQUIPMENT and MATERIALS transport:

*	Main dimensions

*	Displacement

*	Power

*	Maximum speed

*	No. of passengers

*	R.I.N.A. seaworthiness certificate up to the limit inclusive of rig location being set up

*	Rescue equipment

*	Endurance.

This vessel may be made available to COMPANY according to availability.

If the shuttle is supplied by COMPANY, it is established that loading CONTRACTOR's MATERIALS and EQUIPMENT thereon and customs documents shall be done by CONTRACTOR at its expense.

15.2.2.	Transportation Barge:

*	Name

*	Main dimensions

*	Characteristics

*	Equipment

*	Flag

*	Tonnage

15.2.3.	 Towboat for towing Barge:

*	Name

*	Power

*	Maximum speed

*	Equipment

*	Flag

*	Tonnage

*	Bollard pull.

In addition to the foregoing, for all vessels CONTRACTOR shall deliver a copy of:

- Certificate of fitness for the transport of goods and (waste)

- Name of the vessel

- Owners

- Register number of  vessel

- Name of  international vessel

- Authorization to carry X-ray sources

15.3.	The prices and rates of the vessels under the CONTRACT include the costs relating to crew (on the basis of relevant “fitting-out tables”), bunkers, maintenance, repair and revision works, agency, shelter, mooring, transit fees, insurance of the vessels and crew and any other costs that are not expressly cited herein.

15.4.	The vessels shall carry out transports and/or activities they are equipped for in compliance with the provisions supplied by COMPANY; any liability for their management and use shall rest with the Pilot, as prescribed by applicable legislation and all expenses and consequences resulting from any fact or event shall be charged to CONTRACTOR and may not be charged to COMPANY, except for wilful misconduct or gross negligence of COMPANY.

15.5.	CONTRACTOR may request COMPANY to replace the vessels originally proposed and approved by COMPANY, provided that CONTRACTOR proves the  impossibility to use them due to causes and faults not attributable to CONTRACTOR and occurring after the award of the CONTRACT. The characteristics and capabilities of the new vessels shall not be below those of the vessels being replaced and shall in any case be re-approved by COMPANY. The PARTIES agree that any additional charge and cost resulting from the replacement of the vessels, in respect of the resulting changes of the WORK, shall be fully charged to CONTRACTOR.

16.	CUSTOMS ACTIVITIES

16.1.	For customs activities connected with exportation offshore, pursuant to art. 132 of Presidential Decree no. 43 dated 23.1.1973, CONTRACTOR shall agree with the appropriate customs Office, at the COMMENCEMENT DATE OF THE WORK or upon the setting up of the CONSTRUCTION SITE, the modalities of assessment of the weight of MATERIALS and/or WORK to be exported and/or the documents to be produced and submitted. The bill of entry shall be in the name of CONTRACTOR.

The foregoing refers to MATERIALS, whether processed or not by CONTRACTOR, and to WORK carried out by CONTRACTOR and MATERIALS delivered to CONTRACTOR by COMPANY in accordance with the provisions contained in the CONTRACT.

16.2.	All expenses for customs documents, including those relating to COMPANY-owned MATERIALS used by CONTRACTOR, shall be charged to CONTRACTOR. All reimbursements of customs duties and other duties on exported products (export bonus) shall be for CONTRACTOR’s benefit.

16.3. CONTRACTOR's invoice bearing the note “Materials for offshore export” and “Not subject to VAT (art. 8 of Presidential Decree dated 26th October 1972 no. 663 and art. 132 of Presidential Decree dated 23rd January 1973 no. 43)” shall be sent to COMPANY,  one (1)  original and four (4)  copies, including one stamped by the Customs Office and bearing the bill of export details.

16.4.	All formalities and expenses for the temporary or final export of CONTRACTOR's MATERIALS and EQUIPMENT shall be charged to CONTRACTOR.

16.5.	Any delays in the commencement of customs activities and/or in the obtainment of the necessary export authorizations, resulting in an extension of the term under the CONTRACT for the END DATE OF THE WORK shall be deemed delays attributable to CONTRACTOR and, therefore, no extensions may be granted by COMPANY.

17.	DELIVERY OF THE AREA FOR THE COMMENCEMENT OF THE WORK

17.1.	When delivering the area where the WORK shall be performed COMPANY shall also fix the COMMENCEMENT DATE OF THE WORK at the CONSTRUCTION SITE upon which the terms of progress and completion thereof shall be effective, in compliance with the provisions contained in the CONTRACT.

The above-mentioned date shall be written on the “Commencement date of the work report” that the PARTIES' REPRESENTATIVES shall sign and that will become a probative document of the CONTRACT.

Delivery of the AREA OF OPERATIONS may also take place separately for each lot of the WORK and at different times.

17.2.	If, for reasons due to COMPANY, or due to the lack of permits, concessions or authorizations by the appropriate public authorities, delivery of the area takes place later than the date previously agreed, CONTRACTOR may only be granted  a corresponding extension period.

If the above-mentioned delay lasts longer than 180 (one-hundred eighty) calendar days, the PARTIES shall meet to establish the new schedule and to agree on a revision formula for the prices and/or rates under the CONTRACT.

17.3.	For no reason may CONTRACTOR delay the COMMENCEMENT DATE OF THE WORK without the prior authorization by COMPANY under penalty of CONTRACT termination under Art. “Termination with Cause”.

18.	INSPECTIONS - TESTS

18.1.	COMPANY will be entitled at any time to check any part of the WORK and to carry out or cause THIRD PARTIES to carry out inspections and tests on the WORK and MATERIALS, whether they are held in store or being used, and may also consult and/or photocopy the CONSTRUCTION SITE books of account, the “Works Register” and the other documents that CONTRACTOR shall keep at the CONSTRUCTION SITE under applicable legislation. CONTRACTOR may not object to said inspections and tests, but shall give all the necessary assistance to facilitate the performance thereof, free of charge.

18.2.	In addition, in no case may CONTRACTOR object to having THIRD PARTIES authorized by COMPANY or Bodies and Organizations carrying out police, tax, administrative, technical, environmental formalities by law inspect the CONSTRUCTION SITE. On the contrary, CONTRACTOR shall facilitate the performance of the inspections, without any extra amounts charged to COMPANY.

Non-authorized personnel and/or people not being part of the above-mentioned Bodies and Organizations may not access the CONSTRUCTION SITE.

18.3.	Any objection raised  emerged during  the inspections and tests by COMPANY shall be recorded  in the “Works Register”, or notified in writing to CONTRACTOR and, both COMPANY's objections and those made by the Bodies and Organizations set forth in clause 18.2, if relating to wrongful conduct, poor organization and non-compliance with any obligation by CONTRACTOR, shall be settled by CONTRACTOR, at its expense, without causing any hindrances and/or delays to the WORK or direct or indirect damage to COMPANY. Any damage shall in any case be charged to CONTRACTOR which shall indemnify it within 90 (ninety) days from the date of the debit note.

19.	GOOD PRESERVATION OF THE WORK PERFORMED

CONTRACTOR shall arrange, at its expense, for the good preservation and maintenance of the parts of WORK performed, until the date of the report of taking receipt of the WORK in Art. “Testing and taking receipt of completed work”.

Until that date, the cost of all repair and restoration activities required to keep those parts in perfect conditions of preservation shall be charged to CONTRACTOR.

The expenses relating to said activities shall be included in the prices and/or rates under the CONTRACT.

If CONTRACTOR does not arrange for the foregoing, COMPANY shall directly carry out the repairs and/or maintenance works required, charging CONTRACTOR with any additional amount to the value or repair and/or maintenance works carried out and the reimbursement received by COMPANY's Insurance Companies. CONTRACTOR shall make the relevant payment within 90 (ninety) days from the date of the debit note.

20.	TESTING AND TAKING RECEIPT OF COMPLETED WORK

20.1.	Once the WORK is completed, CONTRACTOR shall immediately notify COMPANY thereof in writing; COMPANY, in conjunction with CONTRACTOR, shall make a site inspection in order to assess whether  the WORK is acceptable and it can take receipt of it.

The testing activities shall be carried out no later than  sixty (60) calendar days from the notice of the END DATE OF THE WORK sent by CONTRACTOR.

Those activities shall also imply the technical control-audit aimed at determining, among other things, the exact scope of the WORK performed by CONTRACTOR and therefore the total amount due by COMPANY to CONTRACTOR.

20.2.	Testing shall be carried out by CONTRACTOR at its expense in the presence of COMPANY's REPRESENTATIVE; the relevant expenses shall be included in the prices and/or rates under the CONTRACT, excluding COMPANY's REPRESENTATIVE's fees.

In case of successful testing, and after obtainment by COMPANY of the valid DURC - “Documento Unico di Regolarità Contributiva” (Unified Document Certifying Payment of Insurance Contributions) relevant to CONTRACTOR, a proper report shall be drawn up to be signed by the PARTIES' REPRESENTATIVES.

In lieu of the obtainment of the DURC “ex officio” by COMPANY, the same may however request CONTRACTOR to submit the aforesaid document.

If, on the contrary, defects and/or deficiencies and/or other faults are found not due to the MATERIALS supplied by COMPANY, CONTRACTOR shall remove them at its expense and within the times established by COMPANY. If CONTRACTOR fails or delays to do so, COMPANY shall arrange for it on its own, charging CONTRACTOR with the relevant expenses; CONTRACTOR shall make the payment within 90 (ninety) days from the date of the debit note.

20.3.	If CONTRACTOR does not agree with the test results, CONTRACTOR may express its reservations on the appropriate report, but it may not prevent COMPANY from taking receipt of the WORK, nor from performing such activities as COMPANY may deem essential in order to make the WORK acceptable.

If the PARTIES do not reach a final agreement on the above-mentioned reservations, Art. “Competent Jurisdiction” shall apply; at the same time, COMPANY shall pay to CONTRACTOR the amount due according to the “End date of the work report”.

If CONTRACTOR delays in signing the “ End date of the work report” by over 15 (fifteen) days, said report shall be deemed accepted by CONTRACTOR.

20.4.	After successful testing, COMPANY shall take receipt of the relevant WORK.

20.5.	Successful testing will release any sums retained by COMPANY as per Art. “Payment Modalities and Invoicing", but shall not release CONTRACTOR from its obligations under CONTRACT, until expiry of the guarantee period, nor shall it release CONTRACTOR from the liabilities established by applicable legislation on the matter.

20.6.	The exact technical procedures to carry out the test shall be described in the technical/management documentation.

If in respect of certain parts of the WORK, such as radio-phone connections, it is necessary to comply with special regulations and to have testing supervised by authorized Bodies or Organizations, the agreements with said Bodies or Organizations shall be the responsibility of CONTRACTOR at its expense.

21.	START-UP TESTS – RUNNING SIMULATIONS

COMPANY shall request CONTRACTOR to make start-up tests and running simulations, if necessary. COMPANY shall indicate the work team needed, as well as the modalities and alleged duration of the activities.

The payment due to CONTRACTOR for the activities carried out by those teams shall be proportioned to hourly or daily rates, or, if the number of people and working days or hours involved are specified, payment shall be calculated on a lump-sum basis.

CONTRACTOR may not refuse to carry out the above-mentioned activities, unless they lie outside its specific technical skills.

22.	CHANGES

22.1.	At any time COMPANY will be entitled to instruct CONTRACTOR in writing, also notwithstanding articles 1660 and 1661 of the Italian Civil Code, to make changes to the type and characteristics of the WORK as well as their performance scheme.

If said changes lead to an increase or a reduction in costs and/or a change in the set delivery schedule, the PARTIES will agree on new prices and/or delivery schedule according to fair criteria and consistent with any provisions set out in the CONTRACT on the matter.

The above will be ratified by COMPANY’s Procurement Function by means of a revision of the CONTRACT.

22.2.	CONTRACTOR may make the above-mentioned changes only upon written request by COMPANY.

All changes made by CONTRACTOR, on its own initiative and without prior authorization and/or acceptance by COMPANY, will require, besides compensation for damages, CONTRACTOR’s obligation to restore the WORK to the conditions provided for by the CONTRACT. The fees related to said actions will be charged to CONTRACTOR.

22.3.	If CONTRACTOR does not comply with the provisions set out in clause 22.2 above, COMPANY reserves the right to terminate the CONTRACT under Art. “Termination with Cause”.

22.4.	The operational/management methods for CONTRACT changes are set out in the procedure cited in Appendix “D”.

23.	PARTIES' REPRESENTATIVES

23.1.	CONTRACTOR'S REPRESENTATIVE

CONTRACTOR shall notify COMPANY in writing of its REPRESENTATIVE's name.

23.2.	COMPANY'S REPRESENTATIVES

23.2.1.	COMPANY shall notify CONTRACTOR in writing of its REPRESENTATIVE's name.

COMPANY's REPRESENTATIVE shall also notify CONTRACTOR of the name of its CONSTRUCTION SITE REPRESENTATIVE ("COMPANY's Construction Site Representative”).

23.2.2.	"COMPANY's Construction Site Representative” shall only check CONTRACTOR’s exact application and full compliance with the contractual conditions and shall not assume any liability for the CONSTRUCTION SITE management and the WORK.

In particular, and except as otherwise specified herein below, “COMPANY’s Construction Site Representative” shall:

a)	define with CONTRACTOR the detailed schedule for the WORK performance within the times contractually established and check compliance with said schedule;

b)	verify, in the performance of the WORK, full correspondence of the MATERIALS supplied by CONTRACTOR;

c)  inspect and record jointly with CONTRACTOR's REPRESENTATIVE the WORK performed;

d)	have CONTRACTOR perform, at its expense and in the presence of COMPANY's representatives, any verification (such as surveys, sampling and relevant technological testing etc.) of the WORK performed;

e)	accept the WORK or refuse the WORK that, at his discretion, is not compliant with best technical practices or the specifications of the CONTRACT;

- sign the CONSTRUCTION SITE documents under the CONTRACT.

23.2.3.	For the performance of the provisions in paragraphs 23.2.1. and 23.2.2., COMPANY's REPRESENTATIVES shall have the right to access, at any time and under any circumstance, CONTRACTOR's warehouses and the AREA OF OPERATIONS, to carry out all those inspections that, in their opinion, are deemed necessary.

23.2.4.	All notices or provisions supplied to CONTRACTOR's REPRESENTATIVE by COMPANY's REPRESENTATIVES shall not release CONTRACTOR from its liabilities for proper performance of the WORK and strict compliance with contractual obligations.

24.	WORKS REGISTER AND LOG-BOOK

24.1.	Throughout the duration of the CONTRACT, CONTRACTOR shall draw up and constantly update a “Works Register” as provided for in the Management Specification, and in particular it shall indicate:

24.1.1.	the names, number and qualification of the employees involved in the WORK;

24.1.2.	the number and type of the main EQUIPMENT delivered to the AREA OF OPERATIONS;

24.1.3.	the name of the place where the WORK is being performed;

24.1.4.	the “work progress” achieved on that day at the facilities concerned;

24.1.5.	weather conditions;

24.1.6.	the provisions received that day from COMPANY;

24.1.7.	any other fact and/or condition affecting the routine performance of the WORK.

The “Works Register” shall be signed by COMPANY's REPRESENTATIVE at the end of every day or, at the latest, on the following day and shall be a probative document in the event of a dispute between the PARTIES.

For vessels activities CONTRACTOR shall hold a proper "Log-Book" as required by applicable legislation.

24.2.	Any reservations on the WORK raised by CONTRACTOR during performance thereof, except for those relating to the measurement of the WORK, as set forth in Art. “Accounting documents – Accounting and reservations", shall be recorded on the “Works Register” forthwith.

In no case may the performance of the WORK by CONTRACTOR be suspended or delayed as a result of any such reservations..

Supporting documentation of any reservations raised by CONTRACTOR shall be sent to COMPANY within 15 (fifteen) days from recording on the “Works Register”. Reservations filed after the above-mentioned 15 (fifteen) days will not be taken into consideration.

COMPANY reserves the right to deal with CONTRACTOR's reservations and remarks after WORK completion.

Any COMPANY's reservations, remarks or observations concerning the CONSTRUCTION SITE, shall also be recorded on the “Works Register”.

24.3.	COMPANY may at any time consult the “Works Register” and “Log-Book” or request a copy thereof from CONTRACTOR.

25.	CONTRACTOR’S OBLIGATIONS

In addition to any other charges/obligations specified as being for COMPANY’s account in Art. “Company's Obligations”, CONTRACTOR shall provide and/or arrange and/or meet the cost of the following.

Irrespective of their impact on the WORK, said obligations shall be included in the prices and/or rates under the CONTRACT.

CONTRACTOR's obligations include but are not limited to:

25.1.	All charges in respect of: mobilization to the AREA OF OPERATIONS, and subsequent demobilization on the END DATE OF THE WORK, of all EQUIPMENT, barracks, tools and in general all CONSTRUCTION SITE equipment required for the performance of the WORK, in respect of lodging, hygiene and health of personnel,   storage of EQUIPMENT and MATERIALS and in general of the erection of the CONSTRUCTION SITE.

25.2.	All charges connected with: the preparation of the area where CONTRACTOR may locate the CONSTRUCTION SITE;  fencing the area (if necessary); erecting any access roads and all the temporary works required both for the performance of the various WORK activities,  transit and safety at the workplace;  the installation of day-time and night-time signs, protections on water streams, electrical lines, piping (both air and underground);  erecting pollution-preventing works in compliance with applicable legislation; repairs and cleaning up of the areas for CONSTRUCTION SITE demobilization.

25.3.	Except as otherwise specified in the Special Conditions, all charges in respect of temporary occupation of areas other than those made available by COMPANY and all expenses for any damage caused to crops and expenses incurred to restore those areas.

25.4.	All charges in respect of the erection of its CONSTRUCTION SITE barracks and all that is essential for the preparation of the area or the platform concerned and disassembly and/or demolition on the END DATE OF THE WORK of all the work that CONTRACTOR has erected and/or built for its CONSTRUCTION SITE requirements.

25.5.	Unless otherwise specified in the Special Conditions, the supply of water and energy for the activities needed to perform the WORK.

25.6.	All charges in respect of electrical (if CONTRACTOR does not set up its generator sets), water, radio-telephone, sewage connections etc. for CONSTRUCTION SITE activity and for the performance of the WORK and all expenses for supply and exhaust lines, consumption etc. Any such charges also include the supply of electrical energy and driving force required for the operation of the EQUIPMENT and for lighting the CONSTRUCTION SITE.

25.7.	All charges to equip the CONSTRUCTION SITE with equipment, medicines and first-aid medicaments, to give the employees means and protection devices to prevent injuries and illnesses, in compliance with applicable legislation.

25.8.	All charges in respect of the guardianship of the AREA OF OPERATIONS, including MATERIALS, EQUIPMENT and anything else stored therein.

25.9.	Salary, withholding taxes, insurance, welfare and accident prevention contributions, for all the employees involved in the WORK, in compliance with applicable legislation, the national collective labour agreement in force for the relevant sector and the specific labour agreements applicable to CONTRACTOR.

CONTRACTOR undertakes to effect payment of salaries to its employees, during the execution of the CONTRACT, by bank transfer. Such method of payment shall be used also by SUBCONTRACTORS with regard to their employees.

The documentation proving the execution of the bank transfers mentioned above, with relation to CONTRACTOR’s employees and SUBCONTRACTORS’ employees, shall be kept for the whole duration of the CONTRACT and submitted to COMPANY on request.

25.10.Fees for the assessment of the health status and fitness for work of its employees.

25.11.Compensatory rest times for its employees and related replacement during said times.

25.12.Fees in respect of  the insurance policies set out in Art. “Insurance”.

25.13.All charges in respect of  the supply, loading, transportation, unloading and storage at the CONSTRUCTION SITE of all CONTRACTOR's MATERIALS and EQUIPMENT, as well as the supply and storage at the CONSTRUCTION SITE of all consumables and products required for the maintenance and repair of CONTRACTOR's EQUIPMENT and for the subsistence of its personnel and SUBCONTRACTORS' personnel, including mobilization within the CONSTRUCTION SITE.

25.14.All charges in respect of the supply, loading, transportation, storage and mobilization of fuels, lubricants, oils and greases needed to operate the EQUIPMENT and of the habitability of the CONSTRUCTION SITE barracks.

25.15.All charges in respect of the  reception at the CONSTRUCTION SITE or collection at the delivery points of the MATERIALS to be supplied by COMPANY, loading, transportation, unloading, mobilization and storage at the CONSTRUCTION SITE, including any expense incurred in preserving the MATERIALS and in  drawing up and keeping loading/unloading documents, goods in process account, goods held in store etc.

25.16.All charges for CONTRACTOR's and SUBCONTRACTORS' employees transfers to and from their usual residence at the CONSTRUCTION SITE, and for all local and non-local transfers in connection with the WORK, including fees for the availability and operation of vehicles and/or vessels.

25.17.All charges in respect of the delivery by COMPANY of a furnished office (including a telephone for local/trunk calls and the use of a computer, or a printer, and fax) at the CONSTRUCTION SITE barracks and a berth on board CONTRACTOR's vessels.

25.18.All charges in respect of board and lodging of CONTRACTOR's and SUBCONTRACTORS' personnel and  board for one COMPANY's REPRESENTATIVE staying on the vessels or working on  platforms where no canteen is available.

NOTE:

If COMPANY has any requirements other than berth under clause 25.17 and board for one REPRESENTATIVE under clause 25.18, CONTRACTOR shall meet them. Additional berth and board shall be paid for by COMPANY at the prices and/or rates under the CONTRACT and, in the absence thereof, at the prices and/or rates agreed by the PARTIES.

25.19.All charges in respect of the review of the deliverables of COMPANY's WORK and  CONTRACTOR's drawings, studies, analyses and calculations needed to perform the WORK, including office, stationery, consultancy expenses and expenses connected with the authorizations from appropriate Bodies and Organizations such as the Civil Engineering department, R.I.NA., ISPESL etc.

25.20.All charges in respect of technical staff, supporting manual labourers, EQUIPMENT and MATERIALS needed for checking and testing activities, excluding those relating to personnel designated by COMPANY.

25.21.All charges in respect of the checking  (jointly with COMPANY) of the WORK performed and the supplies made and for drawing up, keeping and updating the CONSTRUCTION SITE accounting documents.

25.22.All charges in respect of scraps and their removal  from the CONSTRUCTION SITE on the END DATE OF THE WORK.

25.23.All charges in respect of customs clearance, if necessary.

25.24.All charges incurred as a result of breaching regulations against pollution of soil, air and water and those connected with the conservation of the environment.

25.25.All charges due to injuries, death, damage and loss in excess of the limits of the insurance policies under paragraphs 31.1.1., 31.1.2. and 31.1.6.

25.26.All charges incurred in arranging insurance against damage to and/or loss of the EQUIPMENT, MATERIALS, and in general of the property of CONTRACTOR,  SUBCONTRACTORS and  of their respective personnel during the WORK and transportation thereof.

25.27.All additional expenses connected with faults, mistakes, negligence and misconduct of CONTRACTOR and in any case all expenses not covered by the insurance policies under the CONTRACT.

25.28.All charges in respect of works, repairs and replacements necessary as a result of assembly errors, defects in CONTRACTOR'S MATERIALS and failures found  during and after the performance of the WORK and until the end of the guarantee period.

25.29.All charges in respect of trials, checks and tests on CONTRACTOR'S MATERIALS and of the repetition by CONTRACTOR of the destructive and non-destructive tests, due to the poor performance of the WORK.

25.30.All charges resulting from CONTRACTOR's non-compliance with laws, rules and regulations in force (including sea legislation and COMPANY's provisions for the WORK to be performed at its plants and platforms).

25.31.All charges caused by disputes arising between CONTRACTOR and the other Companies present at the  CONSTRUCTION SITE.

25.32.All charges borne in enlisting the services of specialized Agencies to assess the vessels' condition, to be performed both before departure and after return thereof to CONTRACTOR's pier, including expenses of repairing damage to the vessels, in case of transportation by CONTRACTOR.

25.33.All charges of preparing the vessels  to load the WORK  or the MATERIALS supplied to CONTRACTOR by COMPANY, including any expenses in respect of reinforcements, supports, tracks, temporary enlargement works and  anything needed to make the vessels fit for the activities that they shall perform, including costs of down-time during the above-mentioned operations and during subsequent repairs, in case of transportation by CONTRACTOR.

25.34.All charges connected with the loading of the vessels and  the materials required for hoisting the WORK on board the vessels, including any expenses in respect of vessels stand-by during loading and unloading activities.

NOTE:  Transfer of CONTRACTOR's EQUIPMENT and MATERIALS from the vessel to the platform and vice-versa and transfer of the WORK performed by CONTRACTOR, if this is possible by using platform cranes or temporary winches; these activities shall be carried out by CONTRACTOR, and COMPANY shall not be charged therefor.

Regarding any items that cannot be hoisted by cranes and winches, transfer to the platform shall be taken care of by COMPANY using its vessels and at its expense.

25.35.All port charges, agency rights, mooring and pilotage expenses as well as all charges connected with lay-by and transit of vessels used by CONTRACTOR, in the case of transportation by CONTRACTOR.

25.36.All charges in respect of the vessels needed to transport the WORK, including any extra costs for change or replacement of vessels in accordance with clause 15.5, if transportation is entrusted to CONTRACTOR.

25.37.All charges in respect of the vessels needed to guard the platforms and to deal with emergency situations.

25.38.All charges in respect of  downtime of work teams, EQUIPMENT, vessels as well as the whole CONSTRUCTION SITE not attributable to orders, faults or causes of COMPANY, including those due to bad weather and sea and to force majeure events.

25.39.All charges of delivering to COMPANY the technical documentation under the CONTRACT, the Final Dossier of the manuals (on paper and magnetic medium) and updated drawings as-built at the end of the WORK.

25.40.All charges in respect of the collection and transportation to the closest COMPANY's CENTRES of surplus and recovered MATERIALS  owned by COMPANY.

25.41.All charges of loading, carrying and unloading waste MATERIALS to an authorized waste disposal site, including expenses of finding said waste disposal site and of paying disposal right thereto.

25.42.All charges in respect of maintenance and  preservation of the WORK performed by CONTRACTOR until COMPANY takes receipt thereof, without prejudice to the obligations connected with the guarantee.

25.43.All charges relating to CONTRACTOR supporting COMPANY for the performance of additional tests on the WORK, if any.

25.44.Any other provisions contained in COMPANY's technical/management documentation.

  - The expense incurred by CONTRACTOR in conducting any site inspection requested by COMPANY shall be included in the prices quoted to COMPANY in the tender.

  - Except as otherwise specified in the Special Conditions, CONTRACTOR shall be charged with the formalities and expenses for any occupation of THIRD PARTIES' land for its requirements and the charges for any damage to THIRD PARTIES' property other than the areas made available by COMPANY. The occupation is in any case subject to COMPANY's prior authorization.

  - All expenses (contractually provided as being for CONTRACTOR’s account) in respect of transportation and/or mobilization of surplus materials owned by COMPANY   shall be included in the prices and/or rates under the CONTRACT; therefore COMPANY shall not pay any additional reimbursement.

  - In case of performance of the WORK at COMPANY’s facilities and/or AREA OF OPERATIONS, CONTRACTOR, upon COMPANY’s request, shall notify COMPANY of the names of:

    - Employer (identified for the management of the activities pursuant to the CONTRACT);

    - Manager/s (identified for the management of the activities pursuant to the CONTRACT);

    - Supervisor/s (identified for the management of the activities pursuant to the CONTRACT);

    - Prevention and Protection Officer.

25.49.Fixed and variable overheads covering all the necessary charges for the running of the Company, borne to pursue the corporate purpose and to comply with the statutory obligations, including, but not limited to, the expenses for the upkeep of the sites, for any type of equipment, for the staff (such as administration, Personnel function etc.) and for managers who do not hold executive offices.

25.50.CONTRACTOR undertakes to promptly notify COMPANY of any changes to the articles of association or the company by-laws or the individuals who manage the Company, also for the purposes of application of the regulations for organized crime prevention.

25.51.Issue of any WORK PERMITS (as defined in the Appendix “E” - HSE-QR Requirements) and authorisations for CONTRACTOR’s personnel, vehicles and support equipment to enter the CONSTRUCTION SITE.

NOTA: L’emissione da parte dell’APPALTATORE dei Permessi di Lavoro è da introdurre nel caso di intervenuta consegna formale (tramite comodato o verbale di consegna sottoscritto) del CANTIERE da parte del COMMITTENTE.

20.52.	Keeping, compilation, subscription of all the documentation related to any WASTE (as defined in the Appendix “E” - HSE-QR Requirements) resulting from the performance of the CONTRACT, for the purpose of  a proper WASTE management in compliance with the applicable legislation.

NOTA: tale previsione va introdotta come a carico dell’APPALTATORE nel caso di rifiuti per i quali lo stesso si configuri come Produttore secondo quanto dettagliato in Allegato E.

______________________________________________________________________

Nota: nel caso di Contratti chiusi che prevedono attività in ambienti sospetti di inquinamento o ambienti confinati di cui al DPR 177/2011, integrare il presente Articolo con la clausola di seguito riportata.

20.53.In case of activities under the Presidential Decree no. 177 of 2011, CONTRACTOR shall provide COMPANY, upon COMPANY’s request and prior to commencement of the activities, with the list of workers that CONTRACTOR intends to employ in such activities and relevant  training certificates already provided by CONTRACTOR to COMPANY at the time of the CONTRACT award.

______________________________________________________________________

Nota: nel caso di Contratti aperti che prevedono attività in ambienti sospetti di inquinamento o ambienti confinati di cui al DPR 177/2011, integrare il presente Articolo con la clausola di seguito riportata.

20.53.In case of activities under the Presidential Decree no. 177 of 2011, CONTRACTOR shall provide COMPANY, prior to commencement of the activities, with the list of workers that CONTRACTOR intends to employ in such activities and the relevant training certificates.

_____________________________________________________________________

(Nota: nel caso di Contratti di valore superiore ai 1.500 Euro,  integrare il presente Articolo con la clausola di seguito riportata)

25.53.CONTRACTOR undertakes to immediately inform both COMPANY and the “Prefecture – Territorial Public Office” (“Prefettura-Ufficio territoriale del Governo”) of the territory where COMPANY is based, in case CONTRACTOR has knowledge of any non-compliance by its counterparty with the financial flow traceability obligations as required by the Law no. 136 of 2010 as amended.

_____________________________________________________________________

- COMPANY’S OBLIGATIONS

In addition to any other charges/obligations specified herein as being for COMPANY’s account, COMPANY shall provide and/or arrange and/or meet the cost of the following:

26.1.	Delivery to CONTRACTOR of the technical documentation, if required, for the performance of the WORK.

26.2.	Delivery to CONTRACTOR of a service area for CONSTRUCTION SITE requirements (excluding guardianship) if the WORK is performed on land belonging to COMPANY or found by COMPANY, or on COMPANY's platforms.

26.3.	 Supply of water, free of charge, at water mains placed at the CONSTRUCTION SITE (excluding supply pipes), only if the WORK is performed on lands or platforms belonging to COMPANY and depending on actual availability.

26.4.	 Use of radio devices, free of charge, placed at the CONSTRUCTION SITE or on the platform only for compulsory operating requirements.

26.5.	Obtaining the authorizations from the appropriate Authorities and/or Public and/or private Entities, as well as permits, grants, servitudes etc. required in relation to the performance of the WORK.

26.6.	Assisting CONTRACTOR in the fulfilment of customs formalities; COMPANY shall not assume any liability therefor. Assistance shall offered by COMPANY's Offices located at the AREA OF OPERATIONS and where those offices are located.

26.7.	Fees in respect of the services of the Inspector designated by COMPANY.

26.8.	Fees in respect of the activities of its employees involved in the WORK.

26.9.	The insurance policies set out in Art. “Insurance”.

26.10. Prior to commencement of the activities under the CONTRACT, delivery to CONTRACTOR of any additional technical documentation supplementary to the DUVRI, as well as the information on the site risks and in any case on the major HSE aspects related to the performance of the CONTRACT,  containing any further risk prevention and protection measures to be adopted to eliminate and/or minimize risks caused by interferences connected with the specific nature of the activities under the CONTRACT, which are unforeseeable at the time of conclusion of the CONTRACT.(see NOTE 1)

NOTE 1: Inserire la clausola 26.10 ove applicabile. La consegna delle informazioni rilevanti ai fini HSE dal Committente all’Appaltatore deve essere tracciata mediante firma per accettazione da parte dell’Appaltatore.

26.11.	Issue of any WORK PERMITS (as defined in the Appendix “E” - HSE-QR Requirements) and authorisations for CONTRACTOR’s personnel, vehicles and support equipment to enter the AREA OF OPERATIONS or the CONSTRUCTION SITE.

NOTA: L’emissione da parte del Committente è da introdurre nel caso in cui l’AREA DEI SERVIZI o il CANTIERE non sono stati consegnati formalmente all’APPALTATORE

  - Keeping, compilation, signing of all the documentation related to WASTE management (as defined in Appendix “E” - HSE-QR Requirements).

NOTA: tale previsione va introdotta come a carico del Committente nel caso di rifiuti per i quali il Committente si configuri come Produttore secondo quanto dettagliato in Allegato E Requisiti HSE-QR).

- HEALTH, SAFETY AND ENVIRONMENT 	*(SEE NOTE 1)

27.1.	The WORK shall be performed in compliance with all the rules on workers’ health and safety protection, public safety and protection of environment from pollution and/or radiation protection as provided for by the regulations in force.

COMPANY has delivered to CONTRACTOR, and CONTRACTOR declares to have formally accepted, the documentation related to health and safety in the workplace, including DUVRI, DSSC, PSC and COMPANY’s HSE Policy, as detailed in the Appendix “E” -HSE-QR Requirements, as well as the measures of prevention and emergency measures adopted in relation to the activities carried out in the CONSTRUCTION SITE. In particular, such documentation refers to the specific risks of the environment where CONTRACTOR and/or SUBCONTRACTORS shall carry out their activities, as also regulated by COMPANY in-house policy and procedures concerning safety, health and environment. COMPANY will timely send to CONTRACTOR any update/revision to any reference documents previously delivered.

CONTRACTOR undertakes to cause its employees and any SUBCONTRACTORS’ employees to comply with all the rules and provisions in force in the workplace, regulations and measures contained in the aforesaid documentation, COMPANY’s HSE-QR Requirements attached to the CONTRACT, as well as the regulations for protection of health and safety of employees in the workplace under Legislative Decree no. 81/2008 as amended and Legislative Decree no. 624/1996 as amended, where applicable.

HSE-QR documentation specified in the Appendix “E”- HSE-QR Requirements, which CONTRACTOR shall prepare in respect of the SERVICE (Integrated Quality Plan and documents cited therein) shall be submitted to COMPANY for acceptance.

Without prejudice to CONTRACTOR’s liabilities, COMPANY reserves the right to confirm in writing the acceptance of said documentation within 30 (thirty) days from receipt thereof by CONTRACTOR. After said period has gone without COMPANY’s sending a reply in writing to CONTRACTOR, the documents prepared by the latter will be considered as accepted. Acceptance of said documentation does not result in COMPANY’s assuming any liability for the failure to apply the provisions contained in said documentation or the wrong application thereof.

Should any problems on ionizing radiations occur, CONTRACTOR shall comply with the provisions set out in Appendix “E”- HSE-QR Requirements, in the Special Conditions and any provisions set out by COMPANY, as established by specific documentation on the matter, and delivered to CONTRACTOR.

CONTRACTOR shall also immediately report any accident and/or injury, including minor ones, at the workplace to any Authorities and Entities provided for by the regulations in force, as well as to COMPANY itself.

CONTRACTOR also undertakes to provide on a monthly basis the CONTRACT ADMINISTRATOR, and the Unit in charge of HSE-QR management, with the overall number of worked hours at the workplace, as well as the causes, reasons and circumstances of each occurred injury/accident and remedial measures.

27.2. *(SEE NOTE 2) Under art. 26 of Legislative Decree no. 81 of 2008, the PARTIES state that they have met for the purposes of co-operation and co-ordination of the prevention and protection measures related to workers’ health and safety in the workplace. In particular, the meeting between the PARTIES included discussion of: 1) Preliminary DUVRI”/”Preliminary Information for the DUVRI  preparation”   attached to the Invitation To Tender; 2) the outcome of the site inspection carried out by CONTRACTOR at the workplaces in which the contracted activities are to be performed.

In consideration of the above, the PARTIES have identified the interferences and defined prevention and protection measures to eliminate and/or minimize such interferences, which have consequently been included in the DUVRI attached to the CONTRACT.

_______________________________________________________________

Nota: nel caso di Contratti che prevedono attività in ambienti sospetti di inquinamento o ambienti confinati di cui al DPR 177/2011, sostituire il precedente paragrafo con il seguente

In consideration of the above, the PARTIES have identified the interferences and defined prevention and protection measures, also in relation to the activities under Presidential Decree no. 177 of 2011, to eliminate and/or minimize such interferences, which have consequently been included in the DUVRI attached to the CONTRACT/WORK ORDER.

________________________________________________________________

Prior to commencement of activities, the co-operation and co-ordination, as well as any actions provided for by the PARTIES, shall be included on a proper Meeting Report signed by the PARTIES, which will assume "pro quota" responsibility for implementation of the prevention and protection measures. Said Report shall constitute an integral and substantial part of the DUVRI.

*(SEE NOTE 3) Under art. 9 of Legislative Decree no. 624 of 1996, CONTRACTOR shall deliver to COMPANY the necessary documentation so that COMPANY may prepare the "Coordinated Health and Safety Document" (DSSC) according to which CONTRACTOR, subject to prior signing, becomes responsible for the implementation of the part pertaining thereto.

The DSSC is attached to the CONTRACT and kept at the workplace where the WORK is executed, so that the “Titolare” (Manager), as defined in Legislative Decree no. 624 of 1996, may modify and supplement the DSSC in a timely manner.

*(SEE NOTE 4) Under Chapter IV of Legislative Decree no. 81 of 2008, as amended, COMPANY has the right to appoint a Project Supervisor.

CONTRACTOR undertakes to strictly comply with the Safety and Co-ordination Plan (PSC), its own Operational Safety Plan (POS) transmitted to the Execution Co-ordinator and, however, all the plans and/or instructions which will be delivered and/or given thereto by COMPANY, or by the Project Supervisor and/or by the Execution Co-ordinator.

CONTRACTOR shall also coordinate all SUBCONTRACTORS working at COMPANY’s worksite in order to make the specific POS’s prepared by the individual SUBCONTRACTORS compatible with one another and consistent with the POS submitted by CONTRACTOR.

During the performance of the contracted activity, CONTRACTOR shall adopt all cautions, measures and actions needed to avoid any injury or damage to people or property and co-operate to take risk prevention and protection measures on the activity covered by the CONTRACT.

27.3.	Without prejudice to the provisions of the HSE Disciplinary Policy as per Appendix “E”- HSE-QR Requirements, in case of failure by CONTRACTOR and any SUBCONTRACTORS to comply with the regulations set out in the aforesaid Appendix “E”, in the DUVRI, including any failure to prove the expenditure of the interference-related costs as declared therein,  or in the PSC and/or their own POS, or in the DSSC and/or the procedures and regulations adopted by COMPANY in the workplace, as well, in general, the applicable legislation concerning workers’ health and safety protection and/or environmental protection and/or radiation protection, COMPANY reserves the right to:

27.3.1.	terminate the CONTRACT under Art. “Termination with Cause”, provided that CONTRACTOR shall be liable for any damage, accident or injury which might occur during the performance of the WORK or as a result thereof;

27.3.2.	discontinue the WORK to the detriment of CONTRACTOR charging CONTRACTOR with any extra costs resulting therefrom.

27.4.	COMPANY reserves the right to perform inspections and assessments, also in case of any accidents and injuries, both by its corporate functions and by THIRD PARTIES. In case any non-compliance is found, COMPANY may at its own discretion apply adequate sanctions as provided in the Appendix “E”- HSE-QR Requirements. CONTRACTOR shall collaborate for the achievement of the aforesaid objectives. Moreover, COMPANY reserves the right to request any suitable documentation proving the expenditure by CONTRACTOR of the interference-related costs of safety at work.

27.5.	Without prejudice to the  role of COMPANY as WASTE PRODUCER (PRODUTTORE dei RIFIUTI) (as defined in Appendix “E” - HSE-QR Requirements), CONTRACTOR shall be considered WASTE PRODUCER with regard to the management of any debris/WASTE resulting from maintenance and use of CONTRACTOR’s means, equipment, devices, etc, and deriving from the performance of CONTRACTOR’s activity. CONTRACTOR undertakes to carry out at its own costs any movement and/or service of such materials, within and outside the  CONSTRUCTION SITE and/or CONSTRUCTION SITE AREA, to authorised WASTE DISPOSAL areas or plants (as defined in Appendix “E” - HSE-QR Requirements), in compliance with the applicable legislation  according to the WASTE nature and characteristics, and, with regard to the movement and management of the WASTE produced within the CONSTRUCTION SITE and/or CONSTRUCTION SITE AREA, in compliance with both any in-house regulations and the provisions of Legislative Decree 152/2006 and Ministerial Decree 17/12/2009, as amended.

__________________________________________________________

(Nota: ove applicabile, inserire la seguente formulazione nelle Condizioni Specifiche)

Without prejudice to CONTRACTOR’s obligations to strictly comply with any provision contained in the HSE Disciplinary Policy  as per the Appendix “E”- HSE-QR Requirements, with any other provision contained in the aforesaid Appendix “E”, in the DUVRI, or the PSC and/or its  own  POS, or the DSSC, any procedures and regulations adopted by COMPANY in the workplace, and in general any regulations in force regarding protection of the workers’ health and safety and/or environmental protection and/or radiation protection, CONTRACTOR will be paid a bonus of …… in case of……….

______________________________________________________________

28.5.	Costs relevant to safety at work

28.5.1.	 CONTRACTOR has indicated and/or supplemented the interference-related costs of safety at work in the “Risk identification and Contractor’s prevention and protection measures” Form. CONTRACTOR ensures that such costs are adequate and no rebate has been applied thereto. COMPANY has verified that such costs are commensurate with the nature and characteristics of the activities under the CONTRACT.

28.5.2.	(SEE NOTE 5) CONTRACTOR declares that interference- related costs relevant to safety at work have been calculated also taking into consideration the “Preliminary DUVRI”/,“Preliminary Information for the DUVRI preparation” attached to the Invitation To Tender, the final DUVRI, where applicable, or the PSC, or the DSSC and relevant technical documentation, the verifications carried out by CONTRACTOR during the site inspection (where appropriate), and any other documentation and information obtained further to the co-ordination and co-operation as per art. 26 of Legislative Decree no. 81/2008, as well as any in-house procedures and regulations delivered to CONTRACTOR.

27.6.	Costs of labour

CONTRACTOR declares that costs of labour are commensurate with the nature and characteristics of the activities under the CONTRACT.

### Nel caso di Contratti che prevedono attività in ambienti sospetti di inquinamento e negli ambienti confinati di cui al DPR 177/2011, integrare il presente Articolo con la clausola di seguito riportata.

27.7. Activities in potentially contaminated areas and confined spaces

The activities in potentially contaminated areas and confined spaces shall be performed in accordance with the provisions of Presidential Decree no. 177 of 2011. In particular, CONTRACTOR shall meet the qualification requirements as per Art. 2 of the aforesaid Decree.

Throughout the performance of the activities in potentially contaminated areas or confined spaces, CONTRACTOR shall use and effectively implement a working procedure specifically aimed at eliminating or, if impossible, minimizing the risks of activities in confined spaces, inclusive of any first aid and coordination with the emergency system of the National Health Service ("Servizio Sanitario Nazionale") and the Fire Fighting Department ("Vigili del Fuoco").

Also, before entering the areas where said activities will be conducted, all workers employed by CONTRACTOR, including the Employer ("Datore di lavoro") if part of the team performing these activities, or any self-employed worker, shall be informed by COMPANY of the characteristics of the workplaces, the risks existing therein (including those deriving from previous uses of the workplace) and the prevention and emergency measures taken in connection with its activities.

COMPANY identify its own Representative, with appropriate skills, acquainted and aware of the risks existing in the workplaces, so that the Representative shall supervise, direct and coordinate the activities carried out by the workers employed by CONTRACTOR or any self-employed worker, in order to minimize any risks  connected with interference of such activities with those performed by COMPANY personnel.

# NOTA 1: Applicabile per Servizi resi presso la sede del COMMITTENTE.

NOTA 2: Applicabile per i Servizi resi ai sensi del D.Lgs. n. 81 del 2008 per l’esecuzione dei quali è prevista l’elaborazione del DUVRI.

# NOTA 3: Applicabile per i Servizi resi ai sensi del D.Lgs. n. 624 del 1996.

NOTA 4: Applicabile per Lavori resi all’interno di un cantiere temporaneo o mobile di cui al Titolo IV del D. Lgs. n. 81 del 2008.

NOTA 5: I riferimenti relativi ai costi della sicurezza trovano applicazione anche con riferimento alle attività svolte in luoghi di lavoro che non rientrano nella disponibilità giuridica del COMMITTENTE, nonché per attività soggette alla disciplina di cui al D.Lgs. n. 624 del 1996.

- RADIATION SOURCES

28.1.	Without prejudice to Art. “Health, Safety and Environment" for radiological protection of the workers present at the AREA OF OPERATIONS and the Population living in neighbouring areas, CONTRACTOR shall comply, in as far as applicable, with clauses 28.2, 28.3, 28.4 and 28.5.

28.2.	Before starting any activities entailing the use, in areas under COMPANY’s control, of radiation sources belonging to CONTRACTOR, CONTRACTOR shall provide COMPANY with a copy of the notice previously sent (at least 15 days before the beginning of the use of the sources at a given area) to the Supervisory Bodies having jurisdiction over the relevant territory and a copy of the specific report on radiation protection, produced by the Qualified Expert engaged by CONTRACTOR, on the occurrence of the conditions set out in paragraph 7 Appendix IX of Legislative Decree 230/95, as amended.

28.3.	CONTRACTOR, when working in the presence of COMPANY-owned radioactive sources and in areas pertaining to COMPANY’s responsibility, shall comply with the directions given by COMPANY and with the rules contained in the current provisions on workers’ (its own workers, COMPANY’s workers or the equivalent) and Population’s radiological protection.

28.4.	If CONTRACTOR’s activity has as its scope the radioactive sources used in activities operated by COMPANY and constitutes a specialist service, CONTRACTOR shall be fully liable for the activities performed and the consequences resulting therefrom, holding COMPANY harmless against any liability, including vis-à-vis THIRD PARTIES.

28.5.	CONTRACTOR shall abide by any Operating Procedures and COMPANY's Management Specification in addition to applicable legislation on radiation protection.

- CONTRACTOR'S REQUIREMENTS

29.1.	CONTRACTOR represents that the WORK will be performed using the necessary means and managing them at its own risk and it may use SUBCONTRACTORS as described in Art. “Subcontracting”.

CONTRACTOR may also make use of agency-supplied workers in full compliance with the applicable legislation.

If CONTRACTOR decides, during the performance of the CONTRACT, to make use of the above-mentioned agency-supplied workers, it undertakes to notify the CONTRACT ADMINISTRATOR of said intention and to state the reasons, number of workers, activities concerned, as well as to deliver, if so requested, the related contract.

29.2.	With regard to the above, CONTRACTOR will perform the WORK assuming all liabilities both vis-à-vis COMPANY and the Public Authorities and THIRD PARTIES, holding COMPANY harmless against claims of any type which arise out of the performance of the WORK.

29.3.	CONTRACTOR shall prove to be in possession of all authorizations and licences required to work in its capacity as "contractor" and undertakes to constantly work in compliance therewith and with the current legislation on the matter.

29.4.	In case of irregularity in CONTRACTOR's administrative and/or legal position resulting from non-compliance with the above requirements, COMPANY shall have the right to terminate the CONTRACT as stated in Art. “Termination with Cause”.

  - Throughout the duration of the CONTRACT, CONTRACTOR shall meet:

- the general requirements under art. 38 of Legislative Decree no. 163/2006, as amended;

- the necessary technical and professional requirements with reference to protection of health and safety in the workplace, under art. 26, paragraph 1, letter a) or art. 90, paragraph 9 of Legislative Decree no. 81/2008, based on the activities contracted.

- CONTRACTOR undertakes to timely communicate to COMPANY any variation to the information and documentation delivered to COMPANY.

  - COMPANY reserves the right to request CONTRACTOR to submit any certification proving fulfilment of the requirements as aforesaid   and, however, to ascertain, at its discretion and at any time, even autonomously, that such requirements are fulfilled.

In the event of failure by CONTRACTOR to meet even one of the above requirements, COMPANY reserves the right to terminate the CONTRACT pursuant to Art. “Termination with cause”.

- PARTIES' LIABILITIES

Pursuant to art. 1229 of the Italian Civil Code, it is agreed that the limits of liabilities provided for in the following clauses of this Article will not be applicable in case of damage due to wilful misconduct or gross negligence by COMPANY or by CONTRACTOR.

In case of wilful misconduct or gross negligence by COMPANY or by CONTRACTOR, they will remain therefore liable for the damage caused and will indemnify and hold the other PARTY harmless from and against any claim for damages arising out of wilful misconduct or gross negligence.

30.1. All liabilities for the performance of the WORK, up to taking receipt by COMPANY, shall be fully charged to CONTRACTOR and no consequences and charges resulting from events occurred at the CONSTRUCTION SITE and/or at sea may be attributed nor charged to COMPANY, whatever their cause, without prejudice to the liabilities herein below.

Liabilities assumed by COMPANY are only set forth in the CONTRACT. Therefore, no additional liabilities may be attributed to COMPANY, even in case of omissions or incomplete listing of CONTRACTOR's liabilities. Any amendments shall be set forth in the Special Conditions.

30.2.	CONTRACTOR shall be responsible for the skills and fitness of anyone and anything involved in the WORK, and shall be liable for all events adversely affecting the performance of the WORK due to deficiency, inefficiency, unfitness etc. of anything introduced in the CONSTRUCTION SITE.

30.3.	CONTRACTOR shall be solely liable for any damage to and/or loss of the EQUIPMENT/MATERIALS and/or goods belonging to CONTRACTOR, its employees and SUBCONTRACTORS and in any case to staff engaged by CONTRACTOR for the WORK.

30.4.	CONTRACTOR is solely liable for any injury to, illness or death of its personnel, SUBCONTRACTORS’ personnel and agency-supplied personnel, whatever the cause, whether it occurred during the performance of the WORK, or during any transport.

CONTRACTOR shall indemnify and hold COMPANY and its personnel harmless from and against any expense, loss or liability due and/or related to those injuries, illnesses, deaths, whatever the cause.

30.5.	CONTRACTOR is solely liable, whatever the cause, for any damage, loss, destruction, injury, illness or death, caused to THIRD PARTIES (including damage and/or loss caused to COMPANY's plants and/or property) by CONTRACTOR, by SUBCONTRACTORS and by the agency-supplied personnel used by CONTRACTOR.

CONTRACTOR shall indemnify and hold COMPANY and its personnel harmless from and against any claim, request or action by THIRD PARTIES, resulting from or connected to the WORK.

30.6.	CONTRACTOR shall be liable for any damage arising out of pollution or contamination (including control and removal thereof) caused by CONTRACTOR due to the spillage on the surface of fuels, lubricants, paints, solvents, radioactive materials, waste or other polluting substances, in the possession, or under the control, of CONTRACTOR.

CONTRACTOR shall therefore indemnify and hold COMPANY harmless from and against any claim by THIRD PARTIES resulting therefrom.

30.7.	Without prejudice to CONTRACTOR's liabilities referred to in clauses 30.1. and 30.5., COMPANY, notwithstanding the level of deductibles contemplated by the policies effected in compliance with paragraphs 31.2.1. and 31.2.4., accepts to indemnify and hold CONTRACTOR harmless from and against any damage to WORK and/or any damage caused by CONTRACTOR to COMPANY's systems and/or property, in excess of:

- Euro 300,000 for each damage to the onshore WORK.

- Euro 500,000 per each damage to the offshore WORK.

-	Euro 3,000,000  for each damage caused to COMPANY's systems and/or property.

Without prejudice to the provisions contained in Articles “Intellectual Property and Patent Right" and “Confidential Information, Administrative Responsibility and Privacy” COMPANY agrees to release CONTRACTOR from any financial liability vis-à-vis THIRD PARTIES for any amount in excess of Euro 3,000,000 per event.

30.8.	Except as provided for in Art. “Health, Safety and Environment” and Art. “HSE-QR Requirements", COMPANY shall be solely liable for any injury to, illness or death of its personnel, whatever the cause.

COMPANY shall indemnify and hold CONTRACTOR harmless from and against any expense, loss or liability due and/or relating to said injury, illness, death.

30.9.	The PARTIES expressly agree that COMPANY and CONTRACTOR will not be held mutually responsible for any damage caused by the loss and/or discontinuance in the use, of equipment, profit, production and business.

30.10.Health, Safety and Environment Liability

CONTRACTOR assumes all expenses and consequences which might arise out of the failure to comply with the rules on workers’ health and safety protection and/or environmental protection and/or radiation protection provided for by the regulations in force, set out in Art. “Health, Safety and Environment”, holding COMPANY harmless from and against any liability, including to THIRD PARTIES.

30.11.Liability for cost assessment

CONTRACTOR is solely liable in case of miscalculation and wrong information however obtained, except for any information received by COMPANY, as set out in Art. “Knowledge of the Area of operations – Site Inspection”. All costs and expenses for CONTRACTOR’s account shall be deemed included in the prices and/or rates under the CONTRACT; therefore no claims for extra payments shall be accepted by COMPANY.

30.12.Liability for non-compliant WORK

If, due to miscalculation, wrong reports and/or interpretations in the WORK, or however for causes attributable to CONTRACTOR, the WORK is not compliant with the contractual requirements, CONTRACTOR undertakes at its expense to make the necessary changes so that the WORK or the deliverables are compliant with the provisions of the CONTRACT, without any charges to COMPANY and without any delays affecting the WORK schedule.

30.13.Liability for failure to comply with the methods and times of performance of the WORK

CONTRACTOR assumes all expenses and consequences which should arise out of the failure to comply with the methods and times of performance of the WORK under the CONTRACT, with the application of penalties where provided for therein.

30.14. Liability for failure to pay salaries, social security contributions, obligatory insurance premiums and tax deductions

CONTRACTOR shall indemnify and relieve COMPANY from responsibility for all amounts the latter should be asked to pay for salaries, social security contributions, obligatory insurance premiums and withholding taxes relevant to CONTRACTOR's personnel and those of any SUBCONTRACTORS, as well as for any damage to said personnel caused by CONTRACTOR or any SUBCONTRACTORS.

31.	INSURANCE

31.1.CONTRACTOR's insurance policies

Without prejudice to the liabilities of CONTRACTOR, as set out in Art. "Parties’ Liabilities", CONTRACTOR shall effect and maintain the following insurance policies throughout the duration of the CONTRACT. The policies shall be effected with insurance companies rated "BBB" or higher by STANDARD AND POOR'S (S&P) or equivalent on the date of CONTRACT award.

CONTRACTOR’s policies shall be sent in duplicate to COMPANY’s Unit in charge of administering the CONTRACT 20 (twenty) days before the commencement of the performance of the WORK.

It is understood that the arrangement by CONTRACTOR of the policies may not in any way change the liabilities assumed by CONTRACTOR under the CONTRACT.

31.1.1.	A policy covering injuries to and/or death of its subordinate employees and its SUBCONTRACTORS’ employees, in compliance with applicable legislation.

In addition to the policies required by the applicable legislation, CONTRACTOR shall maintain a policy covering injuries to and/or death of all its employees and its SUBCONTRACTORS’ employees, with appropriate limits as may be relevant to the WORK and to the categories of employees involved and in any case no lower than six times the amount of the yearly gross remuneration for death and seven times the same amount for permanent disability.

These policies shall be valid also when CONTRACTOR’s employees travel on board of COMPANY’s and/or its contractors’ means.

31.1.2. 	"All Risks" Policy covering CONTRACTOR’s and any SUBCONTRACTORS’ EQUIPMENT and/or MATERIALS up to a limit amounting to the full replacement value thereof.

NOTE:  As specified in paragraph 1.1.3 and subsequently cited in clause 30.3, the PARTIES agree that the Vessels shall be deemed “EQUIPMENT” and shall be insured both against any damage sustained (Hull & Machinery Policy) and against damage caused to THIRD PARTIES (Protection & Indemnity Policy). CONTRACTOR's insurance policies shall establish not only damage repair, but also reimbursement of the costs relating to vessel down-time during damage repair; if the down-time period cannot be covered by the insurance, it shall in any case be deemed charged to CONTRACTOR.

31.1.3.	“THIRD PARTIES LIABILITY” policy up to a limit of Euro 3,000,000 per event.

In this policy COMPANY will act as "Additional Assured".

Said policy shall also include any damage resulting from pollution or contamination caused by CONTRACTOR, and in accordance with the liabilities assumed by CONTRACTOR, set forth in clause 30.6.

31.1.4.	Policy against any damage to and/or loss of the MATERIALS supplied by COMPANY and/or the WORK, whatever the cause, up to the limits set out in clause 30.7.

31.1.5.	Policy against all damage and/or loss caused by CONTRACTOR  to COMPANY's facilities (onshore stations, platforms, sealines, electric cables etc.) with a limit of Euro 3,000,000 per event.

31.1.6.	EMPLOYER’S LIABILITY" Policy”.

Said policy, with a limit of Euro 3,000,000, shall include also any recourse submitted by INAIL (National Insurance Institute for Industrial Accidents) for injuries or accidents to CONTRACTOR’s employees.

31.1.7.	CONTRACTOR's policies shall exclude insurance deductibles charged to COMPANY and other COMPANY’s Contractors.

31.1.8.	Any damage and/or injury exceeding the limits of CONTRACTOR’s insurance policies will always be charged to CONTRACTOR, except as stated in clause 31.2; in this respect, COMPANY shall be considered indemnified and held harmless from and against any charge and liability.

31.1.9.	The cost of the above-mentioned insurance policies shall be considered included in the prices and/or rates under the CONTRACT.

31.1.10.	Waiver of subrogation right

All insurance policies herein which are maintained by CONTRACTOR shall stipulate that the insurance companies waive their right of subrogation against COMPANY and against any other person for which COMPANY is liable or co-liable or with whom COMPANY has a waiver of subrogation agreement. Said waiver will be restricted to liabilities assumed by CONTRACTOR pursuant to the CONTRACT.

Likewise, the policies carried by COMPANY shall establish the express condition that the insurance companies waive their right of subrogation against CONTRACTOR.

31.1.11. 	Insurance liabilities

If the liabilities for any accidents, injuries, deaths, loss or damage are rejected, in whole or in part, by CONTRACTOR’s insurers due to breaches of said policies by CONTRACTOR, or for any other reason or if CONTRACTOR is not able to maintain any one policy hereunder, CONTRACTOR will indemnify and hold COMPANY harmless from and against any claim filed as a consequence of the above-mentioned events, including any attorney’s fees.

31.2.	COMPANY's insurance policies

COMPANY shall effect, at its expense, the following insurance policies:

31.2.1.   a)	“All Risks” and/or C.A.R. (Contractor's All Risks) policy against damage to and/or physical loss of the WORK, including COMPANY's MATERIALS sent to CONTRACTOR in processing account and held in store, sustained while in store, whatever the reasons and/or cause, excluding CONTRACTOR's wilful misconduct and/or gross negligence for the entire value of the WORK.

b)	For C.A.R. policies it will be necessary for CONTRACTOR to obtain certificates of approval by an authorized Institution, relating to the activities set out in the Special Conditions.

31.2.2.  "THIRD PARTIES LIABILITY” policy.

31.2.3. 	Policy covering its employees' injuries in compliance with applicable legislation.

31.2.4.	Policy against all damage and/or loss caused by CONTRACTOR to COMPANY's plants (onshore stations, platforms, sealines, electric cables etc.) in excess of the limit of Euro 3,000,000 as set out in paragraph 31.1.5.

31.2.5.	All the policies cited in this clause 31.2 exclude the subrogation right vis-à-vis CONTRACTOR, except in case of CONTRACTOR's gross negligence and/or wilful misconduct.

32.	SUSPENSION – DISCONTINUANCE OF THE WORK

32.1.	If the WORK is suspended, COMPANY shall specify in writing to CONTRACTOR whether the suspension is only a temporary suspension or the final termination of the WORK.

32.2.	In case of final termination attributable to COMPANY, Art.  “Termination without cause” shall apply.

32.3.	On the other hand, in the case of suspension attributable to COMPANY, or for lack of permits, grants or authorizations by the appropriate public authorities, CONTRACTOR will be granted the following:

32.3.1. a) for CONSTRUCTION SITE demobilization no monies shall be due by COMPANY to CONTRACTOR. On the other hand, CONTRACTOR shall receive payment for remobilization, when re-commencing the WORK, and subsequent CONSTRUCTION SITE demobilization upon WORK final completion. That payment, if not contained in the CONTRACT, shall be agreed between the PARTIES.

The calculation of CONSTRUCTION SITE mobilization and demobilization costs shall be prepared by CONTRACTOR and shall be appropriately documented.

b) If COMPANY instructs CONTRACTOR to leave the EQUIPMENT and MATERIALS at the CONSTRUCTION SITE, it shall make a payment for each working day and each immobilized asset, whose value shall be previously agreed upon between  the PARTIES and in addition to that it shall also pay the expenses that CONTRACTOR shall incur in respect of the guardianship service of its goods, plus any stand by of its employees until they leave the CONSTRUCTION SITE, to be calculated for a maximum 8 (eight) hours/day and only at the prices and/or rates under the CONTRACT for “Work on a time and materials basis”.

Stand-by hours, as well as the level and qualifications of the personnel on stand-by shall be as stated in the “Works Register”.

For personnel remobilization at the end of the suspension and for final demobilization on the END DATE OF THE WORK, the PARTIES shall agree on the relevant payment, unless already set out in the CONTRACT. The calculation shall be prepared by CONTRACTOR and shall be properly documented.

32.3.2.	for the suspension period, including the time needed for CONSTRUCTION SITE remobilization, CONTRACTOR shall be granted a corresponding extension on the END DATE OF THE WORK.

32.3.3.	if the suspension ordered by COMPANY delays the END DATE OF THE WORK under the CONTRACT for a period not exceeding 180 (one-hundred eighty) calendar days, the prices and/or rates under the CONTRACT shall remain unchanged.

32.3.4.	if the suspension, whatever the cause, lasts longer than 180 (one-hundred eighty) days, the PARTIES shall agree a  new schedule and  a formula of revision of the contractual prices and/or rates. In addition, in the case of WORK being divided into lots, the PARTIES shall specify whether the suspension refers to a single lot or the whole WORK duration.

32.3.5.	suspension or final termination shall be certified by proper report to be signed by the PARTIES' REPRESENTATIVES.

32.4.	WORK suspension shall not relieve CONTRACTOR from the obligation of maintaining  the CONSTRUCTION SITE in an efficient condition.

33.	PENALTIES

33.1.	In case of delays attributable to CONTRACTOR on the agreed WORK schedule, COMPANY shall instruct CONTRACTOR in writing to remedy said default within 7 (seven) days from receipt, by CONTRACTOR, of COMPANY’s notice. If, once said period (“grace” period) has gone by, CONTRACTOR has not demonstrated that it has taken the necessary steps to meet the above-mentioned schedule, COMPANY may assign part of the WORK to THIRD PARTIES.

Any extra cost incurred by COMPANY shall be charged to CONTRACTOR. CONTRACTOR shall pay the extra cost, if any, within 90 (ninety) days from the date of submission of the debit note.

33.2.	If, despite in assignment of a portion of the WORK to THIRD PARTIES,, CONTRACTOR delays the completion of the remaining WORK (not due to force majeure events or causes attributable to COMPANY), CONTRACTOR shall pay COMPANY a penalty equal to 0.5%/day (zero point five percent) of the total amount of the above-mentioned remaining WORK up to a maximum of 20 (twenty) days, after which COMPANY may terminate the CONTRACT by application of the conditions contained in Art. "Termination with Cause".

The penalty shall also apply if COMPANY decides not to assign part of the WORK and in that case the penalty shall apply to the total amount of the WORK.

The amounts relating to any "Work on a time and materials basis" shall be subject to no penalty.

33.3.	The days of late delivery subject to penalty shall be indicated in a proper Report of taking receipt of the WORK and COMPANY shall deduct the amount of the penalty from the invoice resulting from the latest "Work Progress Report" (WPR).

If the amount of the penalty is higher than that resulting from the latest "Work Progress Report" (WPR), COMPANY shall charge CONTRACTOR with the difference between the amounts, which CONTRACTOR shall pay within 90 (ninety) days from the date of the debit note.

33.4.	If the CONTRACT provides for a prices and/or rates revision clause and if CONTRACTOR through its fault delays WORK completion beyond the contractual terms, COMPANY shall have the right to discontinue prices and/or rates revision starting from the END DATE OF THE WORK under the CONTRACT, in addition to the above-mentioned penalty.

34.	ACCOUNTING DOCUMENTS - ACCOUNTING AND RESERVATIONS

34.1.	The Accounting Documents that CONTRACTOR shall draw up and keep at the CONSTRUCTION SITE, if deemed necessary by COMPANY, are the following:

-   the measurement register;

-  the list of the qualifications of personnel hired and the list of EQUIPMENT;

-   the list of stock;

-   the account book;

-   a summary of the account book;

-   "Work Progress Report" (WPR);

-   WORK final status.

All forms shall be agreed by the PARTIES or they shall conform to formats prescribed by COMPANY.

34.2.	For the computation of the WORK, the following criteria shall be met:

34.2.1.	WORK “on a unit-price basis” shall be calculated according to the decimal metric system, except as otherwise specified in the Technical Specifications, and shall be computed at the CONSTRUCTION SITE jointly by the PARTIES as they are performed.

If the actual measurements are larger than project measurements, the latter shall be considered valid, except as expressly otherwise authorized by COMPANY.

34.2.2.	WORK “on a lump-sum basis” shall be calculated by percentages on the basis of the actual WORK performed and ascertained jointly by the PARTIES.

34.2.3.	WORK “on a time and materials basis” shall be calculated on the basis of the Daily Reports countersigned by “COMPANY's Representative at the Construction Site”.

In WORK “on a unit-price basis” and “on a lump-sum basis”, unless expressly provided for under the CONTRACT, the MATERIALS and/or WORK not yet installed shall not be computed.

The quantities and percentages of WORK calculated shall be entered in the Account Book, set forth in clause 34.1, and valued by applying the prices and/or rates under the CONTRACT.

34.3.	The Measurement register, set forth in clause 34.1, shall be signed by the PARTIES with or without reservations.

34.4.	The Account Book, set forth in clause 34.1, shall be signed by the PARTIES, with or without reservations.

If CONTRACTOR refuses to sign the Account Book, CONTRACTOR will be requested to do so within a period of 15 (fifteen) calendar days. Thereafter, any continued failure by CONTRACTOR to sign shall be recorded in the Account Book.

In case of signature with reservation, CONTRACTOR shall, within a period of 15 (fifteen) days, explain its reservations, writing and signing the Book and the corresponding claims for compensation and indicate the amount of the compensation to which it deems to be entitled and the reasons for each claim.

COMPANY shall write on the Book its deductions. If CONTRACTOR has signed the Book, within the above-mentioned deadline, or, having signed with reservation, has not subsequently explained its reservations in the manner and within the term as above, the circumstances recorded shall be treated as ascertained and CONTRACTOR's right to enforce at any time and in any manner its reservations or claims shall become null and void. The appraisal of any reservations shall be carried out after the END DATE OF THE WORK and notably at the time of final settlement.

34.5.	The Accounting Documents shall be drawn up and kept by CONTRACTOR according to applicable legislation.

34.6.	The Accounting Documents shall be Kept for COMPANY’s audit for a minimum period of 2 (two) years starting from the END DATE OF THE WORK and, upon COMPANY’ request, CONTRACTOR shall provide COMPANY with a free copy thereof.

Expenses for drawing up and keeping the above-mentioned accounting documents shall be deemed included in the prices and/or rates under the CONTRACT.

35.	WORK ON A TIME AND MATERIALS BASIS

35.1.	"Work on a time and materials basis" consists of minor activities in terms of outlay relative to the global CONTRACT price; these activities shall be carried out by CONTRACTOR upon COMPANY's written request. Work on a time and materials basis is:

35.1.1.	occasional and/or unpredictable (extra works, commissioning, start-up etc.);

35.1.2.	not quantifiable in terms of prices and/or rates under Appendix “A”;

35.1.3.	not clearly definable, at the time of request, so as to allow its pricing on a lump-sum basis.

35.2.	“Work on a time and materials basis” shall be paid for only if expressly ordered in writing by COMPANY's REPRESENTATIVE. “Work on a time and materials basis” shall be recorded on a special Report to be signed by COMPANY's REPRESENTATIVE on the day after the performance of the “Work on a time and materials basis”. The above-mentioned Report shall be issued by CONTRACTOR in duplicate, one copy for each of the PARTIES and shall detail:

-  the reason for the WORK on a time and materials basis;

-  the name and qualification of employees involved;

-  the number and type of EQUIPMENT used;

-  working hours of employees and EQUIPMENT;

-  the date of performance of the WORK on a time and materials basis;

-  the quantity and type of MATERIALS supplied and used;

-  any other significant details regarding the WORK.

The above-mentioned Report shall form the basis of invoicing the "Work on a time and materials basis”. Any “Work on a time and materials basis” or supplies not accompanied by said Report shall not be paid for.

No “Work on a time and materials basis” performed by CONTRACTOR and without the authorization of COMPANY's REPRESENTATIVE, even if deemed essential, shall be paid for.

35.3.	The prices to be applied to the “Work on a time and materials basis" shall be those under the CONTRACT or in any case those subsequently approved by COMPANY in writing.

The prices shall be applied to the times of use of employees and EQUIPMENT plus the times when said employees and EQUIPMENT have been idle for reasons attributable to COMPANY.

The above-mentioned prices include charges for transportation to site of MATERIALS and EQUIPMENT.

35.4.	If the "Work on a time and materials basis" to be performed can be identified beforehand, the PARTIES shall determine by mutual agreement the level of personnel required and the relevant working times.

The agreement shall be in writing and CONTRACTOR shall be bound to comply therewith.

35.5.	Any indication of working times in terms of hourly rates or similar is just for ease of accounting, it being understood that CONTRACTOR's personnel shall always be considered working under the direction of CONTRACTOR both at a technical-organizational level and at a disciplinary level.

35.6.	If the WORK performed is defective due to poor performance and/or CONTRACTOR's fault, CONTRACTOR shall be responsible, at its expense, for the necessary repairs and changes.

36.	SUPPLIES ON A REIMBURSABLE BASIS

36.1.	If COMPANY requests CONTRACTOR to supply MATERIALS whose prices and/or rates are not under the CONTRACT, the provisions contained in the Procedure in force relating to “Variations to the Contract" (Exhibit “D”) shall apply and notably:

36.1.1.	The supply shall always be requested in writing by COMPANY's REPRESENTATIVE, by means of "Work Instructions" (I.S.T.).

36.1.2.	CONTRACTOR shall issue the Request for Variations (R.D.V.) with copies of the tenders received enclosed and, except as otherwise provided for in the Special Conditions, if the total limit of Euro 5,165.00 is exceeded, CONTRACTOR shall enclose documentation certifying that it has carried out a regular market survey, enclosing a copy of the tenders, a copy of the comparative evaluation, indication of the price agreed, technical recommendations etc.

However, before proceeding to make the purchase, CONTRACTOR shall wait for the issue of the "Direction for Variations to the Contract" (D.V.C.) by COMPANY.

All above-mentioned supplies shall be recorded in the accounts and settled to CONTRACTOR at cost, net of VAT, and except as otherwise provided for in the Special Conditions increased by 5% (five percent).

In order to document the cost, CONTRACTOR shall enclose in the Work Progress Reports (SAL) a copy of D.V.C. with copies of the invoices issued by CONTRACTOR's suppliers enclosed.

36.2.	Non-compliance with the provisions contained herein shall lead to COMPANY's refusing CONTRACTOR’s supplies.

37.	NEW PRICES AND/OR RATES

For any new prices and/or rates, not associated to defined quantities and not established by the CONTRACT, the PARTIES shall agree on manners and criteria for their definition which shall be subject to contractual Revision. For any new prices and/or rates associated to defined quantities, please refer to the Procedure in force relating to “Variations to the Contract” cited in Exhibit “D”.

38.	FIXED PRICES AND/OR RATES

38.1.	The prices and/or rates provided for in the CONTRACT are fixed and invariable throughout the duration thereof. Exception is made for the interference-related costs of safety, which shall in any case be reimbursed by COMPANY against submission of relevant documentary evidence by CONTRACTOR.

Therefore, nothing will be owed to CONTRACTOR as price and/or rate adjustment, notwithstanding the occurrence of any  circumstances, including unpredictable ones, which, by affecting anyhow costs, might justify an adjustment of prices and/or rates under the first subsection of art. 1664 of the Italian Civil Code, in the absence of an express exception and other agreement in the CONTRACT.

38.2.	If, however, due to reasons attributable to COMPANY, or non-obtainment of permits, concessions or authorizations of the appropriate public authorities, the WORK continues after the additional period of 180 (one-hundred eighty) days CONTRACTOR may request to have the prices and/or rates  revised in respect of the WORK that it shall perform after the expiry of said additional period. CONTRACTOR shall notify COMPANY of the request to have the prices and/or rates revised within the maximum term of 60 (sixty) calendar days starting from the expiry of the above-mentioned 180 (one-hundred eighty) days; thereafter its right to benefit of the prices and/or rates revision shall expire.

38.3.	The formulas to be applied for the revision of the prices and/or rates are as follows:

A) CIVIL WORK CONTRACT:

T = S x [0.10 + R x (MDO1/MDO0) + R x (MAT1/MAT0) + R x (NOL1/NOL0)]

where:

S = Amounts of WORK “on a unit-price basis” calculated at the  prices and/or rates under the CONTRACT, entered into the “Work progress reports”.

MDO0 = Hourly price of the typical team made up of the individual components of the “labour” parameter set forth in “AA” below and derived from the Civil Engineering office price list or, in the absence thereof, from the price list of the Industrial Association of the province where the WORK takes place, in force on the date the CONTRACT was concluded.

MDO1 = Price of a typical team derived from the prices of the above-mentioned price lists in the quarter when the WORK was performed.

MAT0 = Unit price of each component of the “materials” parameter set forth in "AA" below derived from the prices of the Civil Engineering office price list or, in the absence thereof, from the price list of the Industrial Association of the province where the WORK takes place, in force on the date the CONTRACT was concluded.

MAT1 = Unit price of the “materials” derived from the above-mentioned price lists in the quarter when the WORK was performed.

NOL0 = Unit price of each individual component of the "Rentals" parameter set forth in "AA" below derived from the Civil Engineering office price list or, in the absence thereof, from the price list of the  Industrial Association of the province where the WORK takes place, in force on the date the CONTRACT was concluded.

NOL1 = Unit price of the "Rentals" derived from the above-mentioned price lists in the quarter when the WORK was performed.

R = Incidence percentages of the "Labour" – Materials – Rentals parameters as set forth in “AA” below.

T = Revised amount.

AA - PARAMETER

Labour (typical team**)

- Specialized workers		No. 2

- Skilled workers			No. 2

- Semi-skilled workers		No. 3

-----------

35%		35%

Materials

- Concrete				7%

- Sand				5%

- Basin				2%

- Iron FeB 38K			7%

- Hollow bricks			8%

- Timber				7%

- Slabs/bricks			6%

-----------

42%		42%

Rentals

- Truck					5%

- Concrete mixer				3%

- Crane					5%

-----------

13%		13%

Fixed and invariable percentage		10%

Total								100%

B) MECHANICAL WORKS CONTRACT

T = S x [0,10 + 0,60 x (/) + 0,20 x (M1/M0) + 0,10 x 	(G1/G0)]

where:

S = Amount of the WORKS calculated according to the prices and/or rates under the CONTRACT.

P1 = Index number of the hourly cost of a 3rd category worker, as set forth in the ANIMA bulletin relating to the period when the WORK was performed.

P0 = Index number in force on the date of execution of the CONTRACT.

M1 = Cost of the materials shown in the ANIMA bulletin - hot-rolled products column "=> 80mm. beams and bars" relating to the period when the WORK was performed.

M0 = Cost of materials in force on the date of execution of the CONTRACT.

G1 = Cost of gas oil published by the Ministry for Productive Activities on the date of execution of the WORK.

G0 = Cost of gas oil published by the Ministry for Productive Activities on the date of execution of the CONTRACT.

T = Revised amount.

C)  ELECTRICAL-INSTRUMENTAL WORKS CONTRACT

T = S x [0.10 + 0.80 x (L1/L0) + 0.10 x (M1/M0)]

where:

S = Amount of the WORK calculated according to the prices and/or rates under the CONTRACT.

L1 = Average hourly payroll cost as shown in the ANIE bulletin – “Changes of wage load” in force on the date of performance of the WORK.

L0 = Payroll cost on the date the CONTRACT was concluded.

M1 = Cost of sundry materials based on the wholesale price list of the Chamber of Commerce of Milan. Index numbers and rate of exchange - Column V - Minerals and Metals, in force on the date of performance of the WORK.

M0 = Cost of materials in force on the date the CONTRACT was concluded.

T = Revised amount.

D) WORK ON A TIME AND MATERIALS BASIS – LABOUR

T = S x [0.10 + 0.90 x (N1/N0)]

where:

S = Amount of the WORK calculated according to the prices and/or rates under the CONTRACT.

N1 = Payroll cost or Index number derived from the category tables indicated in "A" - "B" - "C" above and in force on the date of performance of the WORK.

N0 = Payroll cost or Index number derived from the above-mentioned tables and in force on the date the CONTRACT was concluded.

T = Revised amount.

NOTE:

The EQUIPMENT and operating means, excluding the worker, supplied for “Work on a time and materials basis", shall not be subject to a revision of prices and/or rates.

38.4.	The calculation of the revision of prices and/or rates shall be made by CONTRACTOR; this calculation shall be submitted to COMPANY together with all supporting documentation and copies of all the official price lists used for calculation.

The amount of prices and/or rates revision may be invoiced by CONTRACTOR after COMPANY has verified and approved the above-mentioned calculation - COMPANY's approval shall be notified in writing.

39.	WORK PROGRESS REPORT

CONTRACTOR shall, at the end of each month, submit to COMPANY a "Work Progress Report - WPR (in triplicate) covering the WORK performed by CONTRACTOR.

SAL shall quote:

39.1.	number and date of WPR;

39.2.	reference number and date of issue of the CONTRACT;

39.3.	code number allocated to CONTRACTOR as shown on the CONTRACT;

39.4.	items billable as listed, numbered and described in the CONTRACT;

39.5.	Job Order” number notified to CONTRACTOR by COMPANY.

COMPANY shall check the WPR and, if found in order, one copy thereof shall be returned to CONTRACTOR duly signed for acceptance. Such acceptance shall be treated as technical acceptance of the WORK, as per Art. “Testing and taking receipt of completed work”.

40.	PAYMENTS

40.1.	COMPANY shall pay CONTRACTOR, as full compensation for the WORK, in accordance with the rates of compensation set forth in Appendix "A" – “Compensation”.

The amounts specified in Appendix “A” - “Compensation” include every and any cost incurred by CONTRACTOR in relation to the CONTRACT, including the costs of the insurance policies in Art. “Insurance”; these amounts are to be considered net of VAT, where applicable, and gross of withholding tax.

Such Appendix will identify, among the possible options (WORK progress, milestone etc.), the one selected.

40.2	Unless otherwise stated in the Special Conditions, COMPANY may, at its option, subordinate payment of the rates of compensation to submission by CONTRACTOR of the documentation certifying that CONTRACTOR has effected payments in relation to salaries, social security and social insurance contributions, as well as payment of withholding taxes in respect of its personnel. In case of subcontracting, CONTRACTOR shall give documentary evidence of such payments in respect of the personnel of its SUBCONTRACTORS.

The above is without prejudice to the verifications which shall be made by the CONTRACT ADMINISTRATOR in relation to fulfilment of said obligations under current legislation. In particular, COMPANY shall obtain the valid DURC (Documento Unico di Regolarità Contributiva) relevant to CONTRACTOR and SUBCONTRACTORS.

In lieu of the obtainment of the DURC “ex officio” by COMPANY, the same may however  request CONTRACTOR, and SUCONTRACTOR through CONTRACTOR, to submit the aforesaid document.

If the DURC shows any failure to fulfil such obligations, COMPANY reserves the right to deduct the corresponding amounts from payment due to CONTRACTOR. COMPANY will pay such amounts directly to the social insurance/industrial injury bodies including, in case of works, the Cassa Edile.

Payment of the rates of compensation is however conditional upon:

40.2.1	fulfilment of CONTRACTOR's obligations under Art. "Subcontracting";

40.2.2	acceptance of the WPR by COMPANY, as stated in Art. "Work Progress Report";

40.2.3	if CONTRACTOR and/or SUBCONTRACTOR are among the entities under articles 73 and 74 of the “Testo unico delle imposte sui redditi” (D.P.R. 22 December 1986, no. 917 as amended), submission by CONTRACTOR of the documentation certifying the fulfilment, by CONTRACTOR and any SUBCONTRACTORS, of the obligations related to payment of withholding taxes in connection with the activities performed under the CONTRACT, due at the date of payment by COMPANY.

Such fulfilment shall be certified through a declaration released by one of the entities listed in art. 35 paragraph 28 of Decree-Law no. 223 of July 4, 2006 as amended or, alternatively, through a self-declaration made pursuant to DPR no. 445 of 28 December 2000, as amended. In particular the self-declaration, issued in accordance with the specimen “Law 134 - Affirmation of Certification” attached to the Invitation to Tender, shall:

- indicate the date of payment of withholding taxes, through total or partial deduction;

- specify the details of the “Model F24” used for payment of the withholding taxes not deducted, totally or partially;

- state that the withholding taxes paid include those relating to the CONTRACT/subcontract in relation to which the declaration is made.

COMPANY may suspend payment hereunder until submission by CONTRACTOR, and subsequent verification by COMPANY, of the aforesaid declaration/self-declaration.

Such declaration/self-declaration shall be released to COMPANY and sent:

- through certified e-mail (PEC) of the person making the declaration, released pursuant to DPR no. 68 of 11 February 2005 as amended, to the following PEC address:

fornitori.l134@pec.eniadfin.it

or, if no PEC is available,

- by fax to the following number:

06 59887527

or, if neither PEC nor fax is available,

- in original on paper form, to the following mail address:

eni spa

Ufficio Contabilità Fornitori Roma

Via del Serafico 200

00142 – Roma

If CONTRACTOR and COMPANY have entered into several contracts, CONTRACTOR shall send to COMPANY a single declaration/self-declaration, with specific statement that the above obligations have been fulfilled in relation to all the above contracts.

The aforesaid declaration/self-declaration shall be issued by CONTRACTOR also in case of assignment of credits to THIRD PARTIES, which assignment shall be expressly authorized by COMPANY.

41.	PAYMENT MODALITIES AND INVOICING

41.1.	The payment of CONTRACTOR’s invoice(s) shall be effected by bank transfer, as specified in Art. “Payments” of the Special Conditions.

41.2.	No payment shall be made by COMPANY to banks other than those designated by CONTRACTOR, unless any change is notified to COMPANY by CONTRACTOR in writing at least 60 (sixty) days in advance.

______________________________________________________________________

(Nota: nel caso di Contratti di valore superiore ai 1.500 Euro, sostituire le clausole 41.1 e 41.2 con le formulazioni di seguito riportate)

41.1.	Both COMPANY and CONTRACTOR shall assume the financial flow traceability obligations as required by art. 3 of Law no. 136 of 2010 as amended.

Therefore, the payment of CONTRACTOR's invoice(s) shall be effected by bank transfer as specified in Art. "Payments" of the Special Conditions.

In relation to any transaction, each bank transfer shall refer to the Tender Identification Code (CIG).

The payment shall be effected to a dedicated bank account of CONTRACTOR, in compliance with the Law no. 136 of 2010 as amended.

To this end CONTRACTOR shall send to COMPANY, by means of an appropriate declaration and within the terms required by Law no. 136 of 2010 as amended, the following information, unless already communicated by CONTRACTOR under any previous contracts: identification details of the dedicated bank account, personal details and fiscal codes of the persons empowered to operate on it.

The above declaration shall be drawn up as per “Law 136-Model 1” form enclosed with the Invitation To Tender and sent by registered mail (return receipt requested) to the following address:

eni S.p.A.

Ufficio Contabilità Fornitori Roma

Via del Serafico 200

00142 Roma

Italia

Copy thereof shall be sent in advance  by fax (No. 0039 06 59880252) or in electronic format (not modifiable PDF file) to the following address: tracciabpag@eni.com.

41.2.	Based on he understanding that all payments under the CONTRACT are conditional upon receipt by COMPANY of the above mentioned declaration, no payment shall be made by COMPANY to dedicated bank accounts/banks other than those designated by CONTRACTOR, unless any change to any details of the previously communicated dedicated bank account is timely notified to COMPANY by CONTRACTOR.

______________________________________________________________________

41.3.	Issuance of CONTRACTOR’s invoice(s) shall be conditional upon receipt of the WPR approved by COMPANY.

41.4.	To the extent possible, the invoice(s) shall relate to one WPR only, or any other document indicated in Appendix "A". Also, it/they shall indicate the number and date of the WPR and be drafted on the basis of the same in terms of format and contents.

41.5.	The VAT rate and amount or the item(s) not subject to VAT shall be shown on the invoice(s.

41.6.	The invoice(s) (one original) shall be sent by priority mail (or equivalent) to the address indicated in Art. "Invoicing" of the Special Conditions.

41.7.	To ensure the efficient settlement of the invoices, any item(s) and/or rates not covered by the CONTRACT shall not be shown on the invoice(s); any such item(s) and/or rates shall be billed separately after definition thereof.

In no case may billings chargeable to different Job Orders be included in a single WPR and/or invoice.

41.8.	If any volume discount is required by the CONTRACT, CONTRACTOR shall issue appropriate Credit Notes in respect thereof.

41.9.	The PARTIES agree that any late payment by COMPANY, caused by CONTRACTOR’s failure to comply with the above provisions and to fulfil the obligations in Art. “Payments”, shall not be treated as COMPANY’s default. Therefore, no interest for late payment shall apply.

41.10.To the extent possible, each invoice shall:

- have a standard format in terms of sheet (vertical A4) and lay-out;

- not be coloured in the fields related to the basic details of the invoice(s).

41.11.To ensure that the invoices are settled when due, the following   details shall be shown on the invoice(s:

41.11.1.	the name and address of the Bank where payment is to be made;

41.11.2.	the name of the bank branch;

41.11.3.	number of current account;

41.11.4.	BBAN code (for national payments);

41.11.5.	IBAN code and BIC code (for international payments).

______________________________________________________________________

(Nota: nel caso di Contratti di valore superiore ai 1.500 Euro,  sostituire la clausola 41.11 con la formulazione di seguito riportata)

41.11. Subject to the above provisions, to ensure that the invoices are settled when due, the following details shall be shown on the invoice(s):

a)  the name and address of the Bank where the dedicated bank account has been opened;

b)	the name of the bank branch;

c)	number of the dedicated bank account;

d)	BBAN code (for national payments);

e)	IBAN code and BIC code (for international payments).

_____________________________________________________________________

41.12.Payment of WORK "on a unit-price basis" and "on a lump-sum basis" shall be made by COMPANY to CONTRACTOR as follows:

a) 90% (ninety percent) upon receipt of the monthly "Work Progress Report".

b) 5% (five percent) upon taking receipt of the WORK, after positive testing.

c) 5% (five percent) at the end of the "Guarantee Period" as defined in the Special Conditions, or upon taking receipt of the WORK after positive testing if CONTRACTOR obtains a "first demand" Guarantee of the same amount in favour of COMPANY securing the good performance of the WORK.

The whole amount of the Guarantee shall be valid and effective up to two months after expiry of the "Guarantee Period", as defined in the Special Conditions.

NOTE: As an alternative to paragraphs 41.12.a), 41.12.b) and 41.12.c) use the following.

a) 100% (onehundred percent) upon receipt of the monthly "Work Progress Report".

b) CONTRACTOR, within 20 days before the commencement of the performance of the WORK, shall obtain at its expense, from a leading Bank or Insurance Company, a “first demand” Guarantee in favour of COMPANY securing the good performance of the WORK.

The amount of the Guarantee shall equal 10% (ten percent) of the amount of the WORK.

The whole amount of the Guarantee shall be valid and effective up to two months after the expiry of the “Guarantee Period”, as defined in the Special Conditions.

c) Payments of the invoices regarding "Work on a time and materials basis", supplies on a reimbursable basis and those relating to loading, hoisting and sea transport, shall be made by COMPANY 100% (one-hundred percent).

42.	NON-ASSIGNMENT OF CREDITS

Unless expressly authorized by COMPANY, the assignment of all credits due to CONTRACTOR under the CONTRACT is excluded under art. 1260, second subsection of the Italian Civil Code, with resulting liability of CONTRACTOR to COMPANY for any breach of the above-mentioned agreement.

Further, in no circumstances may CONTRACTOR give any special cash warrants to any THIRD PARTY(IES), nor delegate, in any manner whatsoever, the collection of any of the monies due to CONTRACTOR hereunder.

43.	GUARANTEES

43.1.	Technical Warranties

43.1.1.	The WORK shall be performed by CONTRACTOR using MATERIALS and according to procedures so as to provide the technical and time warranties set forth in the Special Conditions.

The warranties do not apply to MATERIALS supplied by COMPANY, but are in any case requested for installation and setup carried out by CONTRACTOR.

The warranties shall be effective as from the date of positive testing and/or taking receipt of the WORK, set forth in Art. "Testing and taking receipt of completed work".

43.1.2.	Within the guarantee period, CONTRACTOR shall arrange, at its expense, for all restoring works (repairs, retouching, re-making), required due to the bad performance of the WORK and/or defects of the MATERIALS supplied by CONTRACTOR.

For that purpose, COMPANY shall promptly report to CONTRACTOR the deficiencies found and shall proceed to assess any deteriorations, breakages, failures etc. as well as the determination of the date within which CONTRACTOR shall commence the restoring works and the date within which those works shall be completed.

If, after COMPANY's notice, CONTRACTOR does not carry out the restoring works, COMPANY shall have the right to engage THIRD PARTIES charging CONTRACTOR with the expense incurred, under prior submission of proper supporting documentation. Said expense shall be paid by CONTRACTOR within 90 (ninety) days from the date of the relevant debit note.

43.1.3.	CONTRACTOR guarantees that it has carefully considered and assessed the costs and risks on its account and that it has offered to COMPANY fairly profitable appropriate technical-economic conditions; therefore it shall not have the right, especially after the execution of the CONTRACT, to file claims and/or to claim for indemnifications from COMPANY due to omitted or wrong assessments of the above-mentioned facts, nor may CONTRACTOR in any case fail to meet its contractual obligations.

43.1.4.	The obligations assumed by CONTRACTOR under the CONTRACT shall be deemed terminated upon expiry of the guarantee period. Upon said expiry, COMPANY shall release the money payable to CONTRACTOR under the CONTRACT.

43.2.	INSURANCE AND BANK GUARANTEES

43.2.1.	If so required by the CONTRACT, CONTRACTOR shall obtain at its expense, from a leading Bank or Insurance Company rated “BBB” or higher by STANDARD AND POOR’S (S & P) or equivalent, a “first demand” Guarantee in favour of COMPANY.

The text of the Guarantee shall be written according to Appendix "C".

43.2.2.	In the case set out in paragraph 43.2.1., no payment will be made to CONTRACTOR before acceptance of the Guarantee by COMPANY.

If the Guarantee is not written according to Appendix "C" or the term or guaranteed amount does not correspond to the provisions contained in the CONTRACT or otherwise the Guarantee is not accepted by COMPANY, CONTRACTOR will be forced to make at its expense the necessary adjustments.

43.2.3.	If the duration of the WORK is delayed for causes which are not attributable to CONTRACTOR, the Guarantee, if provided for as set out in paragraph 43.2.1., shall be extended for the same period by CONTRACTOR but at the expense of COMPANY.

Vice-versa, the above-mentioned fees will be charged to CONTRACTOR if the commencement of the WORK is delayed for causes which are attributable to CONTRACTOR.

44.	AUDIT

COMPANY, upon written notice to CONTRACTOR, shall have the right to audit, at any time and up to 10 (ten) years after expiry of the CONTRACT, all invoices and supporting documentation of CONTRACTOR related to the WORK.

CONTRACTOR undertakes to keep detailed and accurate documentation to be supplied to COMPANY for auditing purposes.

45.	TAXES AND DUTIES

45.1.	CONTRACTOR shall arrange payment of all taxes, duties, levies, charges and contributions connected with the CONTRACT as imposed by governmental authorities and/or other authorities having jurisdiction on the CONTRACT.

45.2.	COMPANY does not assume any liability in case of tax defaults by CONTRACTOR which undertakes to strictly abide by the rules in force on the matter.

46.	INSOLVENCY PROCEDURES

In the event CONTRACTOR is submitted to any of the insolvency procedures contemplated by the legislation in force or it is presumed, on the basis of irrefutable evidence, that CONTRACTOR will be submitted to any such procedures, COMPANY reserves the right to terminate the CONTRACT, as set out in Art.  "Termination with Cause".

If this is the case, and where no impediment(s) of a judicial nature exist, COMPANY will only pay for WORK performed by CONTRACTOR, at the rates and prices set forth in the CONTRACT, provided that any such WORK conform to the requirements of the CONTRACT.

No other compensation shall be due to CONTRACTOR by COMPANY.

47.	ASSIGNMENT OF THE CONTRACT

47.1.	Assignment by COMPANY

47.1.1.	CONTRACTOR agrees to the assignment of the CONTRACT, by COMPANY, to THIRD PARTIES or to COMPANY’s AFFILIATES.

Such assignment shall be effective as from the date of COMPANY’s notification thereof to CONTRACTOR.

47.1.2.	assignees will take over all rights and obligations arising out of the CONTRACT from COMPANY.

CONTRACTOR undertakes to obtain all endorsements of the insurance policies needed under the CONTRACT so that the assignees may have, against said insurance policies, the same rights as COMPANY’s.

47.2.	Assignment by CONTRACTOR

47.2.1.	CONTRACTOR may not assign, in whole or in part, the CONTRACT to THIRD PARTIES.

47.2.2.	Failure to abide by the prohibition set out in paragraph 47.2.1 above will result in the immediate termination of the CONTRACT in compliance with the provisions contained in Art. "Termination with Cause", subject to COMPANY’s right to compensation for all damage deriving therefrom and reimbursement of any expenses met.

Alternative A

48.	SUBCONTRACTING

(Versione utilizzabile in ambito di applicazione del D. Lgs. n. 163 del 2006)

The terms “Subcontracting” and “SUBCONTRATTO” used in this CONTRACT shall have the meanings as per art. 118 of Legislative Decree no. 163 of 2006 as amended.

  - On the basis that multi-tier subcontracting is not allowed, in whole or in part, all services, works and supplies of any category may be subcontracted, within the limits and on the conditions provided for by the applicable legislation and according to the conditions indicated herein below.

The limits of subcontracting under this CONTRACT are those indicated in Invitation To Tender and in Art. “Subcontracting” of the Special Conditions.

Regarding works, subcontracting is allowed only for a portion not exceeding 30% (thirty per cent) of the amount of the prevailing category.

Regarding services and supplies, such percentage refers to the total amount of the CONTRACT.

48.2	Subcontracting within the above limits, shall be conditional on the prior written authorization by COMPANY subject to  verification that:

48.2.1	the activities to be authorized for subcontracting have been previously indicated and described at the time of submitting the Tender and, if possible, SUBCONTRACTORS' names have been specified;

48.2.2	SUBCONTRACTOR meets the general requirements under art. 38 of Legislative Decree no. 163 of 2006 as amended;

48.2.3	SUBCONTRACTOR meets the requirements in respect of payment of salaries and Insurance Contributions;

48.2.4	SUBCONTRACTOR meets the necessary technical and professional requirements with reference to protection of health and safety in the workplace, under art. 26, paragraph 1, letter a), or art. 90, paragraph 9 of Legislative Decree no. 81 of 2008, based on the activities subcontracted, as well as any such qualification requirements relevant to the activities subcontracted as are specified in the Invitation to Tender;

48.2.5	where required by applicable law, none of the disqualification cases under art. 67 of Legislative Decree no. 159 of 2011, as amended, nor any attempts at Mafia-related activities as per art. 84 paragraph 4 and art. 91 paragraph 6 of the above Decree no. 159 of 2011, as amended, exist in respect of SUBCONTRACTOR;

48.2.6	the Contract concluded between CONTRACTOR and SUBCONTRACTOR shall include, subject to absolute invalidity of such Contract, a specific clause whereby both parties assume the financial flow traceability obligations required by Law no. 136 of 2010 as amended, and SUBCONTRACTOR undertakes to immediately inform both COMPANY and the “Prefecture–Territorial Public Office” (“Prefettura-Ufficio territoriale del Governo”) of the territory where COMPANY is based, in case it has knowledge of any non-compliance by its counterparty with the financial flow traceability obligations.

To this end CONTRACTOR shall send to COMPANY a declaration, signed by its legal representative and made pursuant to Presidential Decree no. 445 of 2000, whereby CONTRACTOR confirms that the aforesaid clause is included in the Contract concluded between CONTRACTOR and SUBCONTRACTOR. The abovementioned declaration shall be drawn up as per “Model 2” enclosed with the Invitation to Tender;

48.2.7. CONTRACTOR has obtained from SUBCONTRACTOR, and transmitted to COMPANY, SUBCONTRACTOR’s declarations requested in the “Tender Regulations and Conditions Acceptance” Form attached to the Invitation To Tender;

48.2.8.  regularity of declarations contained in the Form for “Self-Certification of General Requirements (Affirmation of Certification)” (version for Subcontractor) attached to the Invitation To Tender.

___________________________________________________

48.3	The request for authorization to subcontracting shall specify, consistent with the information provided in the Tender and in accordance with Art. “Subcontracting” of the Special Conditions, the services, works or supplies to be subcontracted; SUBCONTRACTOR's name, consistent with the information provided in the Tender; the amount of the subcontract agreement and relevant interference-related costs of safety at work. The request shall also contain a specific declaration by CONTRACTOR on the subsistence or non-subsistence of any type of control or connection, under art. 2359 of the Italian Civil Code, with SUBCONTRACTOR.

  - The request for authorization to subcontracting, made as per the “Request for Subcontracting Authorisation” Form, shall include the following documentation, the production of which is a pre-requisite for obtainment of such authorization:

- affirmation of certification of registration with the Chamber of Commerce (C.C.I.A.A.) relevant to SUBCONTRACTOR, drawn up as per Model attached to the Invitation to Tender;

- copy of the subcontract agreement specifying interference-related costs of safety at work;

-	SUBCONTRACTOR’s declaration certifying that it meets the general requirements under art. 38 of Legislative Decree no. 163/2006 as amended, as per aforesaid “Form for Self-Certification of General Requirements (Affirmation of Certification)”;

-	SUBCONTRACTOR’s declaration or certification, in compliance with applicable legislation, certifying that it meets the  necessary technical and professional requirements with reference to protection of health and safety in the workplace, under art. 26, paragraph 1, letter a), or art. 90, paragraph 9 of Legislative Decree no. 81/2008, based on the activities subcontracted;

- certification stating that SUBCONTRACTOR meets the qualification requirements in relation to the activities subcontracted, if required by the Invitation To Tender;

-	CONTRACTOR's declaration on the subsistence or non-subsistence of any type of control or connection, under art. 2359 of the Italian Civil Code, with SUBCONTRACTOR;

-	SUBCONTRACTOR’s declarations as per the aforesaid “Tender Regulations and Conditions Acceptance” Form.

In addition to the documents listed above, for the purposes of subcontract authorisation COMPANY may request CONTRACTOR to submit the valid DURC – “Documento Unico di Regolarità Contributiva” (Unified Document Certifying Payment of Insurance Contributions) relevant to SUBCONTRACTOR.

COMPANY reserves the right to request the submission of such certificate(s) as may be deemed necessary, proving that the above requirements are met by SUBCONTRACTOR and, however, to ascertain, even autonomously, at its sole discretion and at any time, by any lawful means, the truthfulness of the above declarations/certifications.

In any case CONTRACTOR shall submit to COMPANY, before commencement of the activities, the documentation required under art. 26, paragraph 1, letter a) of Legislative Decree no. 81/2008, or art. 90, paragraph 9 of Legislative Decree 81/2008, including the documentation required by attachment XVII thereof, where applicable.

COMPANY shall release the authorisation to subcontracting within the terms provided by art. 118 of the Legislative Decree no. 163 of 2006 as amended.

CONTRACTOR shall guarantee that SUBCONTRACTOR continues to meet such requirements during the term of the subcontract agreement and provide adequate evidence thereof to the CONTRACT ADMMINISTRATOR upon request of the same.

48.5 CONTRACTOR shall adopt, for the subcontracted activities, the same unit prices which were adopted at the time of award, with a reduction not higher than 20% (twenty per cent). CONTRACTOR shall pay SUBCONTRACTOR the safety costs relevant to the subcontracted activities, without any rebate.

48.6	CONTRACTOR  shall send to the CONTRACT ADMINISTRATOR, within 20 (twenty) days from the date of each payment made to CONTRACTOR, a copy of the receipted invoices related to the payments made by CONTRACTOR to SUBCONTRACTOR, with the indication of any amounts withheld by way of guarantee.

Failure by CONTRACTOR to submit the receipted invoices as aforesaid will result in suspension by COMPANY of any further payment to CONTRACTOR.

48.7	CONTRACTOR shall coordinate all SUBCONTRACTORS working at COMPANY’s worksite in order to make the specific POS’s prepared by the individual SUBCONTRACTORS compatible with one another and consistent with the POS submitted by CONTRACTOR.

  - CONTRACTOR shall fully comply, and cause SUBCONTRACTOR to fully comply, with the remuneration provisions and the terms and conditions contained in the national and territorial collective labour agreements in force in the sector and in the area where the activities are performed. CONTRACTOR, and SUBCONTRACTORS through CONTRACTOR, shall submit to the CONTRACT ADMINISTRATOR, before the commencement of the activities, the notifications which were submitted to the social insurance agencies, including Cassa Edile, insurance and industrial injury bodies, as well as one (1) copy of the Operational Safety Plan in compliance with the applicable rules and regulations.

  - For the purpose of payment under the CONTRACT (including payment of works in progress and end of works), COMPANY shall obtain the valid DURC - “Documento Unico di Regolarità Contributiva” (Unified Document Certifying Payment of Insurance Contributions), as well as one (1) copy of the payments, where due, to the joint bodies envisaged by the collective labour agreements, relevant to CONTRACTOR and SUBCONTRACTORS.

In lieu of the obtainment of the DURC “ex officio” by COMPANY, the same may however request CONTRACTOR, and SUBCONTRACTOR through CONTRACTOR, to submit the aforesaid document.

48.10	CONTRACTOR will be held responsible vis-à-vis COMPANY for the accurate performance by SUBCONTRACTORS of all obligations arising out or connected with the CONTRACT.

In particular, CONTRACTOR undertakes to carry out all controls  aimed at ensuring that performance of SUBCONTRACTOR’s activities strictly complies with HSE regulations and the procedures and guidelines adopted by COMPANY. CONTRACTOR shall be liable vis-à-vis COMPANY for any non-compliance/irregularity by SUBCONTRACTOR. CONTRACTOR undertakes to carry out the verification and control activity during the term of the CONTRACT and the performance of the activities hereunder.

48.11 Authorization to subcontracting will be revoked, and CONTRACTOR shall ensure that SUBCONTRACTOR, ceases performance of the activities and clears the site or the area of operations from persons and materials/equipment under its responsibility, in case of occurrence of the following:

- failure by SUBCONTRACTOR to meet even one of the general requirements under art. 38 of Legislative Decree no. 163/06 as amended, or submission of such declarations as prove irregular, false or incomplete;

- failure by SUBCONTRACTOR to meet the necessary technical and professional requirements with reference to protection of health and safety in the workplace, under art. 26, paragraph 1, letter a) of Legislative Decree no. 81/2008, or art. 90, paragraph 9 of Legislative Decree no. 81/2008, based on the activities subcontracted;

- proven existence in respect of SUBCONTRACTOR, where required by the applicable law, of any of the disqualification cases contemplated by art. 67 of Legislative Decree no. 159 of 2011, as amended, or attempts at Mafia-related activities as per art. 84 paragraph 4 and art. 91 paragraph 6 of the above Decree no. 159 of 2011, as amended;

- infringement of the obligations under the previous clauses 48.5 and 48.8;

- failure by SUBCONTRACTOR to meet the requirements as per aforesaid “Tender Regulations and Conditions Acceptance” Form and declarations contained therein.

All cases of revocation of authorization to sub-contracting are without prejudice to COMPANY's right to claim compensation for damages from CONTRACTOR and, where necessary, terminate the CONTRACT.

48.12 Without prejudice to the above, in case of non-fulfilment by SUBCONTRACTOR of the regulations contained in the Appendix “E” – HSE-QR Requirements (including the HSE Disciplinary Policy), the DUVRI, where applicable, or the PSC or the DSSC, as well as, in general, the applicable legislation concerning workers’ health and safety protection and/or environmental protection and/or radiation protection, COMPANY shall have the right to terminate the CONTRACT under Art. "Termination with Cause", subject to COMPANY’s right to compensation for damages.

CONTRACTOR undertakes to include in the sub-contract agreement a similar clause stipulating that non-fulfilment by SUBCONTRACTOR of the regulations contained in the Appendix “E” – HSE-QR Requirements  (and in general the rules in force in the workplace according to in-house procedures and applicable legislation), the DUVRI, where applicable, or the PSC or the DSSC, as well as, in general, the applicable legislation concerning workers’ health and safety protection and/or environmental protection and/or radiation protection, will be considered a material breach and grounds for termination of the sub-contract agreement.

48.13 CONTRACTOR shall cause SUBCONTRACTORS to comply with the provisions of clause “Administrative Responsibility” and ensure that SUBCONTRACTOR has reviewed and has knowledge of the contents of “Management System Guideline for Anti-Corruption” of eni S.p.A., as amended, available on the website www.eni.com. In this connection, a specific clause shall be included in the Contract concluded between CONTRACTOR and SUBCONTRACTOR.

### Nel caso di Contratti che prevedono attività in ambienti sospetti di inquinamento e negli ambienti confinati di cui al DPR 177/2011, integrare il presente Articolo con la clausola di seguito riportata.

48.14	No subcontract shall be allowed, in respect of the activities in potentially contaminated areas and confined spaces, under Presidential Decree no. 177 of 2011, unless expressly authorized by COMPANY and certified pursuant to Legislative Decree no. 276 of 10 September 2003 (Titolo VIII, Capo I), as amended. The provisions of said Presidential Decree no. 177 of the 2011 shall also apply to SUBCONTRACTORS.

_________________________________________________________________

SUBCONTRATTO

The SUBCONTRATTO is not subject to prior authorisation by COMPANY, except for the verifications of compliance with technical and professional requirements with reference to health and safety protection in the workplace pursuant to Legislative Decree no. 81 of 2008, which shall be made by COMPANY prior to commencement of the activities that envisage access to the AREA OF OPERATIONS. In any case, CONTRACTOR shall:

- notify the CONTRACT ADMINISTRATOR of the name of the "Subcontraente" (the Firm/Company concluding the SUBCONTRATTO with CONTRACTOR), the amount of the SUBCONTRATTO, the activities under the "SUBCONTRATTO";

- obtain from the "Subcontraente" (i)the same documentation as required from SUBCONTRACTORS in the CONTRACT and to make the relevant verifications before commencement of the activities under the SUBCONTRATTO; (ii) the declarations as per the “Tender Regulations and Conditions Acceptance” Form;

- guarantee that the "Subcontraente" continues to meet all aforesaid requirements during the term of the "SUBCONTRATTO" and provide adequate evidence thereof to the CONTRACT ADMMINISTRATOR upon request of the same;

- have the "Subcontraente" comply with the regulations contained in the clause “Administrative Responsibility”. CONTRACTOR shall also ensure that the "Subcontraente" has reviewed and has knowledge of the contents of the “Management System Guideline for Anti-corruption” of eni S.p.A., as amended, available on the website www.eni.com. In this connection, a specific clause shall be included in the contract concluded between CONTRACTOR and the "Subcontraente".

CONTRACTOR shall transmit, at least on a three-month basis, the specific “Reporting relevant to Subcontratti” Form attached to the Invitation To Tender, with evidence of verifications made by CONTRACTOR regarding the maintenance by the "Subcontraente" of technical and professional requirements and compliance with the applicable HSE regulations, the general requirements, ethical requirements, requirements regarding payment of salaries and Insurance Contributions and economic-financial requirements, as well as all the other requirements requested of SUBCONTRACTOR.

CONTRACTOR undertakes to include in the SUBCONTRATTO a provision on the basis of which failure by the "Subcontraente" to meet the aforesaid requirements shall result in the termination of the contract between CONTRACTOR and the "SUBCONTRAENTE", subject to COMPANY’s right to compensation by CONTRACTOR for any damage and, if necessary, to terminate the CONTRACT.

CONTRACTOR undertakes to include in the SUBCONTRATTO, subject to absolute invalidity of such contract, a specific clause whereby both parties assume the financial flow traceability obligations required by Law no. 136 of 2010 as amended.

### ______________________________________________________

### Nel caso di Contratti che prevedono attività in ambienti sospetti di inquinamento e negli ambienti confinati di cui al DPR 177/2011, integrare il presente Articolo con la clausola di seguito riportata.

No SUBCONTRATTO shall be allowed, in respect of the activities in potentially contaminated areas and confined spaces under Presidential Decree no. 177 of 2011, unless expressly authorized by COMPANY and certified pursuant to Legislative Decree no. 276 of 10 September 2003 (Titolo VIII, Capo I), as amended. The provisions of said Presidential Decree no. 177 of the 2011 shall also apply to the "Subcontraente".

# Nota per il Buyer:

# All’Art. “Subappalto” delle Condizioni Specifiche si dovranno indicare i seguenti dati: soglia entro cui è ammesso il subappalto, attività da subappaltare, figura aziendale che autorizzerà il subappalto.

# Nei contratti aperti, la soglia entro cui è ammesso il subappalto dovrà essere indicata in termini di valore assoluto anziché di percentuale.

Alternative B

49.	SUBCONTRACTING

(Versione utilizzabile per gli appalti sottosoglia e per gli appalti relativi a servizi “non prioritari (Allegao IIB del D. Lgs.163/2006 e s.m.i.).

Sulla base della specificità del Contratto, si suggerisce comunque di valutare l'opportunità dell'inserimento dell' Alternativa A ovvero dell' Alternativa B)

  - On the basis that neither subcontracting of 100% of the contracted activities nor multi-tier subcontracting, in whole or in part, is allowed, all services, works and supplies of any category may be subcontracted within the limits, if any, set out in the Invitation to Tender and in Art. “Subcontracting” of the Special Conditions and according to the conditions indicated herein below.

The limits of subcontracting under this CONTRACT are those indicated in Invitation To Tender and in Art. “Subcontracting” of the Special Conditions.

49.2	Subcontracting, within the above limits, shall be conditional on the prior written authorization by COMPANY, subject to verification that:

49.2.1	the activities to be authorized for subcontracting have been previously indicated and described at the time of submitting the Tender and, if possible, SUBCONTRACTORS' names have been specified;

49.2.2	SUBCONTRACTOR meets the general requirements under art. 38 of Legislative Decree no. 163 of 2006 as amended;

49.2.3. SUBCONTRACTOR meets the requirements in respect of payment of salaries and Insurance Contributions;

49.2.4	SUBCONTRACTOR meets the necessary technical and professional requirements with reference to protection of health and safety in the workplace, under art. 26, paragraph 1, letter a), or art. 90, paragraph 9 of Legislative Decree no. 81 of 2008, based on the activities subcontracted, as well as any such qualification requirements relevant to the activities subcontracted as are specified in the Invitation to Tender;

49.2.5	where required by applicable law, none of the disqualification cases under art. art. 67 of Legislative Decree no. 159 of 2011, as amended, nor any attempts at Mafia-related activities as per art. 84 paragraph 4 and art. 91 paragraph 6 of the above Decree no. 159 of 2011, as amended, exist in respect of SUBCONTRACTOR;

49.2.6. CONTRACTOR has obtained from SUBCONTRACTOR, and transmitted to COMPANY, SUBCONTRACTOR’s declarations requested in the “Tender Regulations and Conditions Acceptance” Form attached to the Invitation To Tender;

49.2.7.  regularity of declarations contained in the Form for “Self-Certification of General Requirements (Affirmation of Certification)” (version for Subcontractor) attached to the Invitation To Tender.

______________________________________________________________________

(Nota: nel caso di Contratti di valore superiore ai 1.500 Euro,  integrare la clausola 49.2 con il paragrafo di seguito riportato)

49.2.8 the Contract concluded between CONTRACTOR and SUBCONTRACTOR shall include, subject to absolute invalidity of such Contract, a specific clause whereby both parties assume the financial flow traceability obligations required by Law no. 136 of 2010 as amended, and SUBCONTRACTOR undertakes to immediately inform both COMPANY and the “Prefecture–Territorial Public Office” (“Prefettura-Ufficio territoriale del Governo”) of the territory where COMPANY is based, in case it has knowledge of any non-compliance by its counterparty with the financial flow traceability obligations.

To this end CONTRACTOR shall send to the COMPANY a declaration, signed by its legal representative and made pursuant to Presidential Decree no. 445 of 2000, whereby CONTRACTOR confirms that the aforesaid clause is included in the Contract concluded between CONTRACTOR and SUBCONTRACTOR. The abovementioned declaration shall be drawn up as per “Model 2” enclosed with the Invitation to Tender.

______________________________________________________________________

49.3	The request for authorization to subcontractingshall specify consistent with the information provided in the Tender and in accordance with Art. “Subcontracting” of the Special Conditions, the services, works or supplies to be subcontracted; SUBCONTRACTOR's name, consistent with the information provided in the Tender; the amount of the subcontract agreement and relevant interference-related costs of safety at work. The request shall also contain a specific declaration by CONTRACTOR on the subsistence or non-subsistence of any type of control or connection, under art. 2359 of the Italian Civil Code, with SUBCONTRACTOR.

  - The request for authorization to subcontracting, made as per the “Request for Subcontracting Authorisation” Form, shall include the following documentation, the production of which is a pre-requisite for obtainment of such authorization:

- affirmation of certification of registration with the Chamber of Commerce (C.C.I.A.A.) relevant to SUBCONTRACTOR, drawn up as per Model attached to the Invitation to Tender;

- copy of the subcontract agreement specifying interference-related costs of safety at work;

-  DUVRI or PSC or DSS, signed by SUBCONTRACTOR for acceptance;

-	SUBCONTRACTOR’s declaration certifying that it meets the general requirements under art. 38 of Legislative Decree no. 163/2006, as amended, as per aforesaid “Form for Self-Certification of General Requirements (Affirmation of Certification)”;

-	SUBCONTRACTOR’s declaration or certification, in compliance with applicable legislation, certifying that it meets the  necessary technical and professional requirements with reference to protection of health and safety in the workplace, under art. 26, paragraph 1, letter a), or art. 90, paragraph 9 of Legislative Decree no. 81/2008, based on the activities subcontracted;

- certification stating that SUBCONTRACTOR meets the qualification requirements in relation to the activities subcontracted, if required by the Invitation To Tender;

-	CONTRACTOR's declaration on the subsistence or non-subsistence of any type of control or connection, under art. 2359 of the Italian Civil Code, with SUBCONTRACTOR;

-	SUBCONTRACTOR’s declarations as per the aforesaid “Tender Regulations and Conditions Acceptance” Form.

In addition to the documents listed above, for the purposes of subcontract authorisation COMPANY may request CONTRACTOR to submit the valid DURC – “Documento Unico di Regolarità Contributiva” (Unified Document Certifying Payment of Insurance Contributions) relevant to SUBCONTRACTOR.

COMPANY reserves the right to request the submission of such certificate(s) as may be deemed necessary, proving that the above requirements are met by SUBCONTRACTOR and, however, to ascertain, even autonomously, at its sole discretion and at any time, by any lawful means, the truthfulness of the above declarations/certifications.

In any case CONTRACTOR shall submit to COMPANY, before commencement of the activities, the documentation required under art. 26, paragraph 1, letter a) of Legislative Decree no. 81/2008, or art. 90, paragraph 9 of Legislative Decree 81/2008, including the documentation required by attachment XVII thereof, where applicable.

CONTRACTOR shall guarantee that SUBCONTRACTOR continues to meet such requirements during the term of the subcontract agreement and provide adequate evidence thereof to the CONTRACT ADMMINISTRATOR upon request of the same.

49.5 CONTRACTOR shall adopt, for the subcontracted activities, the same unit prices which were adopted at the time of award, with a reduction not higher than 20% (twenty per cent). CONTRACTOR shall pay SUBCONTRACTOR the safety costs relevant to the subcontracted activities, without any rebate.

49.6	CONTRACTOR  shall send to the CONTRACT ADMINISTRATOR, within 20 (twenty) days from the date of each payment made to CONTRACTOR, a copy of the receipted invoices related to the payments made by CONTRACTOR to SUBCONTRACTOR, with the indication of any amounts withheld by way of guarantee.

Failure by CONTRACTOR to submit the receipted invoices as aforesaid will result in suspension by COMPANY of any further payment to CONTRACTOR.

49.7	CONTRACTOR shall coordinate all SUBCONTRACTORS working at COMPANY’s worksite in order to make the specific POS’s prepared by the individual SUBCONTRACTORS compatible with one another and consistent with the POS submitted by CONTRACTOR.

  - CONTRACTOR shall fully comply, and cause SUBCONTRACTOR to fully comply, with the remuneration provisions and the terms and conditions contained in the national and territorial collective labour agreements in force in the sector and in the area where the activities are performed. CONTRACTOR, and SUBCONTRACTORS through CONTRACTOR, shall submit to the CONTRACT ADMINISTRATOR, before the commencement of the activities, the notifications which were submitted to the social insurance agencies, including Cassa Edile, insurance and industrial injury bodies, as well as one (1) copy of the Operational Safety Plan in compliance with the applicable rules and regulations.

  - For the purpose of payment under the CONTRACT (including payment of works in progress and end of works), COMPANY shall submit the valid DURC - “Documento Unico di Regolarità Contributiva” (Unified Document Certifying Payment of Insurance Contributions), as well as one (1) copy of the payments, where due, to the joint bodies envisaged by the collective labour agreements, relevant to CONTRACTOR and SUBCONTRACTORS.

In lieu of the obtainment of the DURC “ex officio” by COMPANY, the same may however request CONTRACTOR, and SUBCONTRACTOR through CONTRACTOR, to submit the aforesaid document.

49.10	CONTRACTOR will be held responsible vis-à-vis COMPANY for the accurate performance by SUBCONTRACTORS of all obligations arising out or connected with the CONTRACT.

In particular, CONTRACTOR undertakes to carry out all controls aimed at ensuring that performance of SUBCONTRACTOR’s activities strictly complies with HSE regulations and the procedures and guidelines adopted by COMPANY. CONTRACTOR shall be liable vis-à-vis COMPANY for any non-compliance/irregularity by SUBCONTRACTOR. CONTRACTOR undertakes to carry out the verification and control activity during the term of the CONTRACT and the performance of the activities hereunder.

49.11 Authorization to subcontracting will be revoked, and  CONTRACTOR shall ensure that SUBCONTRACTOR, ceases performance of the activities and clears the site or the area of operations from persons and materials/equipment under its responsibility, in case of occurrence of the following:

- failure by SUBCONTRACTOR to meet even one of the general requirements under art. 38 of Legislative Decree no. 163/06 as amended, or submission of such declarations as prove irregular, false or incomplete;

- failure by SUBCONTRACTOR to meet the necessary technical and professional requirements with reference to protection of health and safety in the workplace, under art. 26, paragraph 1, letter a) of Legislative Decree no. 81/2008, or art. 90, paragraph 9 of Legislative Decree no. 81/2008, based on the activities subcontracted;

- proven existence in respect of SUBCONTRACTOR, where required by the applicable law, of any of the disqualification cases contemplated by art. 67 of Legislative Decree no. 159 of 2011, as amended, or attempts at Mafia-related activities as per art. 84 paragraph 4 and art. 91 paragraph 6 of the above Decree no. 159 of 2011, as amended;

- infringement of the obligations under the previous clauses 49.5 and 49.8;

- failure by SUBCONTRACTOR to meet the requirements as per aforesaid “Tender Regulations and Conditions Acceptance” Form and declarations contained therein.

All cases of revocation of authorization to sub-contracting are without prejudice to COMPANY's right to claim compensation for damages from CONTRACTOR and, where necessary, terminate the CONTRACT.

49.12 Without prejudice to the above, in case of non-fulfilment by SUBCONTRACTOR of the regulations contained in the Appendix “E” – HSE-QR Requirements (including the HSE Disciplinary Policy), the DUVRI, where applicable, or the PSC or the DSSC, as well as, in general, the applicable legislation concerning workers’ health and safety protection and/or environmental protection and/or radiation protection, COMPANY shall have the right to terminate the CONTRACT under Art. "Termination with cause", subject to COMPANY’s right to compensation for damages.

CONTRACTOR undertakes to include in the sub-contract agreement a similar clause stipulating that non-fulfilment by SUBCONTRACTOR of the regulations contained in the Appendix “E” – HSE-QR Requirements  (and in general the rules in force in the workplace according to in-house procedures and applicable legislation), the DUVRI, where applicable, or the PSC or the DSSC, as well as, in general, the applicable legislation concerning workers’ health and safety protection and/or environmental protection and/or radiation protection, will be considered a material breach and grounds for termination of the sub-contract agreement.

49.13 CONTRACTOR shall cause SUBCONTRACTORS to comply with the provisions of clause “Administrative Responsibility” and ensure that SUBCONTRACTOR has reviewed and has knowledge of the contents of “Management System Guideline for Anti-Corruption” of eni S.p.A., as amended, available on the website www.eni.com. In this connection, a specific clause shall be included in the Contract concluded between CONTRACTOR and SUBCONTRACTOR.

### Nel caso di Contratti che prevedono attività in ambienti sospetti di inquinamento e negli ambienti confinati di cui al DPR 177/2011, integrare il presente Articolo con la clausola di seguito riportata.

49.14	No subcontract shall be allowed, in respect of the activities in potentially contaminated areas and confined spaces, under Presidential Decree no. 177 of 2011, unless expressly authorized by COMPANY and certified pursuant to Legislative Decree no. 276 of 10 September 2003 (Titolo VIII, Capo I), as amended. The provisions of said Presidential Decree no. 177 of the 2011 shall also apply to SUBCONTRACTORS.

_________________________________________________________________

SUBCONTRATTO

The SUBCONTRATTO is not subject to prior authorisation by COMPANY, except for the verifications of compliance with technical and professional requirements with reference to health and safety protection in the workplace pursuant to Legislative Decree no. 81 of 2008, which shall be made by COMPANY prior to commencement of the activities that envisage access to the AREA OF OPERATIONS. In any case, CONTRACTOR shall:

- notify the CONTRACT ADMINISTRATOR of the name of the "Subcontraente" (the Firm/Company concluding the SUBCONTRATTO with CONTRACTOR), the amount of the SUBCONTRATTO, the activities under the "SUBCONTRATTO";

- obtain from the "Subcontraente" (i)the same documentation as required from SUBCONTRACTORS in the CONTRACT and to make the relevant verifications before commencement of the activities under the SUBCONTRATTO; (ii) the declarations as per the “Tender Regulations and Conditions Acceptance” Form;

- guarantee that the "Subcontraente" continues to meet all aforesaid requirements during the term of the "SUBCONTRATTO" and provide adequate evidence thereof to the CONTRACT ADMMINISTRATOR upon request of the same;

- have the "Subcontraente" comply with the regulations contained in the clause “Administrative Responsibility”. CONTRACTOR shall also ensure that the "Subcontraente" has reviewed and has knowledge of the contents of the “Management System Guideline for Anti” of eni S.p.A., as amended, available on the website www.eni.com. In this connection, a specific clause shall be included in the contract concluded between CONTRACTOR and the "Subcontraente".

CONTRACTOR shall transmit, at least on a three-month basis, the specific “Reporting relevant to Subcontratti” Form attached to the Invitation To Tender, with evidence of verifications made by CONTRACTOR regarding the maintenance by the "Subcontraente" of technical and professional requirements and compliance with the applicable HSE regulations, the general requirements, ethical requirements, requirements regarding payment of salaries and Insurance Contributions and economic-financial requirements, as well as all the other requirements requested of SUBCONTRACTOR.

CONTRACTOR undertakes to include in the SUBCONTRATTO a provision on the basis of which failure by the "Subcontraente" to meet the aforesaid requirements shall result in the termination of the contract between CONTRACTOR and the "SUBCONTRAENTE", subject to COMPANY’s right to compensation by CONTRACTOR for any damage and, if necessary, to terminate the CONTRACT.

_____________________________________________________________________

(Nota: nel caso di Contratti di valore superiore ai 1.500 Euro, integrare la clausola “Subcontratto” con il paragrafo di seguito riportato)

CONTRACTOR undertakes to include in the SUBCONTRATTO, subject to absolute invalidity of such contract, a specific clause whereby both parties assume the financial flow traceability obligations required by Law no. 136 of 2010 as amended.

### _____________________________________________________

### Nel caso di Contratti che prevedono attività in ambienti sospetti di inquinamento e negli ambienti confinati di cui al DPR 177/2011, integrare il presente Articolo con la clausola di seguito riportata.

No SUBCONTRATTO shall be allowed, in respect of the activities in potentially contaminated areas and confined spaces under Presidential Decree no. 177 of 2011, unless expressly authorized by COMPANY and certified pursuant to Legislative Decree no. 276 of 10 September 2003 (Titolo VIII, Capo I), as amended. The provisions of said Presidential Decree no. 177 of the 2011 shall also apply to the "Subcontraente".

# Nota per il Buyer:

# All’Art. “Subappalto” delle Condizioni Specifiche si dovranno indicare i seguenti dati: soglia entro cui è ammesso il subappalto, attività da subappaltare, figura aziendale che autorizzerà il subappalto.

# Nei contratti aperti, la soglia entro cui è ammesso il subappalto dovrà essere indicata in termini di valore assoluto anziché di percentuale.

50.	COMPLIANCE WITH THE REGULATIONS ON INSURANCE, CONTRIBUTIONS AND CONTRACTS

50.1.	During the performance of the CONTRACT, CONTRACTOR shall work in abidance by the State regulations, this CONTRACT and any other reference regulations on collective agreements, releasing COMPANY from any breaches.

50.2.	In particular, CONTRACTOR shall, with regard to its employees, comply with the regulations on insurance and contributions, as well as to enforce the current national labour agreement for the specific sector. The above-mentioned employees shall be regularly employed, paid and insured by CONTRACTOR and the applied regulations and salaries shall not be lower than those established in the national labour agreements and other company-specific labour agreements.

50.3.	CONTRACTOR undertakes to send to COMPANY a copy of the following documents related to its employees:

50.3.1.	before the commencement of the activities, the notifications of the commencement of new work which were submitted to INPS (Social Security), INAIL (National Insurance Institute for Industrial Accidents) and Cassa Edile, an entity which is responsible for the implementation of the provisions of national collective labour agreements (in case of a Building Enterprise);

50.3.2.	a copy of the payments of contributions made periodically to INPS, INAIL, Cassa Edile (in case of a Building Enterprise) and the joint bodies which are provided for in the collective labour agreements with enclosed description and documentation of payment (e.g.  reference forms according to product area).

Subject to the provisions above, CONTRACTOR shall at any time, and upon request of COMPANY, prove that it has complied with the above.

50.4.	Employees engaged in Italy by Companies with their registered office in a EU country, excluding Italy.

The employees engaged in Italy by Companies with their registered office in a EU country shall abide by the rules and provisions in force in the European Union and in Italy, in particular with regard to social welfare, national insurance and accident prevention.

In particular, with reference to contracts, insurance and contributions, CONTRACTOR shall supply proper documentation which proves the compliance with the rules on the matter in force in the European Union, in Italy and in the Country of origin.

50.5.	Employees engaged in Italy by Companies with their registered office in a non-EU country.

The employees engaged in Italy by Companies with their registered office in a non-EU country shall abide by the rules and provisions in force in Italy, in particular with regard to social welfare, national insurance and accidents prevention, as well as any other provisions in force in the Country of origin on the matter.

50.6.	CONTRACTOR undertakes to plan personnel turnover in the performance of the CONTRACT.

50.7.	CONTRACTOR undertakes to cause SUBCONTRACTOR to comply, in relation to its employees, with the obligations and charges in line with those undertaken by CONTRACTOR, in particular with reference to the regulations on safety and industrial hygiene as well as the regulations on insurance, contributions and contracts.

50.8.	The PARTIES agree that in case of CONTRACTOR’s failure to meet the requirements covered by this Article, COMPANY may terminate the CONTRACT pursuant to Art. "Termination with Cause".

51.	INTELLECTUAL PROPERTY AND PATENT RIGHT

COMPANY will not be in any way responsible for any damage and claims of any type arising out of alleged or real breaches of intellectual property, patents, trademarks, names or any other rights protected by the law which may arise out of or be caused by or attributed to, directly or indirectly, any WORK performed and/or any equipment used by CONTRACTOR and the latter will indemnify and hold COMPANY harmless from and against said damage and claims.

52.	FORCE MAJEURE

52.1.	The PARTIES will not be held responsible for any non-compliance and/or delays due to force majeure.

Force majeure shall mean exceptional and/or unpredictable events and/or circumstances which, despite their prevention and containment actions, the PARTIES cannot stop, avoid and/or control and which affect fully or partially the performance of the CONTRACT.

52.2.	Force majeure events include, but are not limited to: wars, riots, fires, floods, earthquakes and other exceptional natural events, national and trade strikes, impediments due to specific legislative provisions, other similarly serious impediments which are beyond the PARTIES’ control and are all unpredictable.

Any force majeure event will discontinue the PARTIES’ obligations, but will not affect the CONTRACT validity.

52.3.	All damage suffered by CONTRACTOR arising directly or indirectly out of force majeure events will be charged to CONTRACTOR itself, who may not claim for any compensation and/or indemnification from COMPANY. Likewise COMPANY may not claim for any compensation and/or indemnification from CONTRACTOR for any damage suffered by COMPANY itself as a result of force majeure events.

52.4.	Delays due to the following are not considered force majeure 	events:

52.4.1.	construction site downtime enforced by the competent Authorities due to CONTRACTOR’s failure to abide by the safety rules;

52.4.2.	delays by CONTRACTOR in the supply of materials and/or services;

52.4.3.	delays in delivery by SUBCONTRACTORS;

52.4.4.	rejected materials due to working faults by SUBCONTRACTORS;

52.4.5.	strikes restricted to CONTRACTOR’s plants and employees including micro-conflicts, unrest, as well as the taking part, by CONTRACTOR’s employees, in strikes of any type other than strikes at a national or sector level.

52.5.	Force majeure events shall be notified in writing, promptly and in any case within the 3rd (third) day from occurrence of the event, by the affected PARTY to the other PARTY.

The notice shall provide sufficient explanations on the force majeure event and on its predictable duration.

COMPANY reserves the right to request CONTRACTOR, in addition to a written declaration, to submit a certification by the Chamber of Commerce of the place where the WORK is performed or by any other public authority which is recognized by COMPANY, which certifies the truthfulness of the stated facts pursuant to this clause.

52.6.	For delays caused by force majeure events, CONTRACTOR will be entitled to an extension of the due times proportional to the effect that said delays caused on the course of the WORK.

The extension duration will be agreed by the PARTIES in writing.

52.7.	If the force majeure events continue or are expected to continue for a period longer than 15 (fifteen) days, the PARTIES will meet to determine the criteria for the continuation of the CONTRACT.

52.8.	In case of continuation of the event for over 30 (thirty) days COMPANY will be entitled to terminate the CONTRACT under Art. "Termination with Cause".

In any case CONTRACTOR shall make all efforts to minimise any effects of the force majeure occurrence.

Alternative A

53. 	COMPETENT JURISDICTION

For any dispute which might arise between the PARTIES in relation to the CONTRACT, the place of jurisdiction will be solely the place where COMPANY has its registered office.

Alternative B

54.	DISPUTES – COMPETENT JURISDICTION

(Versione utilizzabile per Contratti Infragruppo)

54.1	Any dispute which might arise between the PARTIES in relation to the CONTRACT, and which has not been amicably settled by the PARTIES, will be submitted to the decision of a Technical Committee of four (4) persons. Each PARTY shall nominate two (2) persons.

The written response of the Technical Committee, decided unanimously, will be binding on both PARTIES. The Technical Committee shall express its response within ten (10) days from the date of relevant request by the PARTIES, unless any extension is granted in writing by the PARTIES.

In case no unanimous response is expressed within the aforesaid period, each PARTY may submit the dispute to the court of competent jurisdiction in ……..2 herein below.

54.2	For any dispute which might arise between the PARTIES in relation to the CONTRACT, and which has not been amicably settled as described in ……..1 above, the place of jurisdiction will be solely the place where COMPANY has its registered office.

55.	GOVERNING LAW

The CONTRACT shall be governed by Italian Law.

56.	AMENDMENTS TO THE CONTRACT

It is understood and agreed by the PARTIES that no amendment to the CONTRACT will be deemed valid unless it is agreed in writing by the PARTIES.

57.	CONFIDENTIAL INFORMATION, ADMINISTRATIVE RESPONSIBILITY AND PRIVACY

57.1.	Confidentiality

CONTRACTOR undertakes to:

57.1.1.	consider all the information under the CONTRACT strictly confidential, to keep it as such and not to disclose it or communicate it to non-authorized individuals, as well as to take all reasonable measures to assure and protect, in whole and in part, and however in any form, the confidentiality of said information, to anyone, except for COMPANY’s units and people in charge;

57.1.2.	refrain from using the information supplied by COMPANY for instrumental purposes;

57.1.3.	refrain from using the information or reproduce it, make excerpts or summaries for other purposes than those related to the CONTRACT.

CONTRACTOR shall comply with the confidentiality agreement herein for three years after CONTRACT termination.

In case of breach, even partial, of the above-mentioned confidentiality agreement, COMPANY, besides the remedy set out in Art. “Termination with Cause”, may claim for suffered damages.

# Alternativa A

(Versione utilizzabile (i) in caso di contratti che prevedono l’esecuzione delle attività in Italia, indipendentemente dalla nazionalità della controparte, oppure (ii) con controparte italiana, indipendentemente dal luogo di esecuzione del contratto)

57.2.	Administrative Responsibility

CONTRACTOR declares to have reviewed and have knowledge of the contents of the document "Model 231", including also the Eni Code of Ethics, drafted by COMPANY in accordance with the legislation in force regarding the administrative liability of legal entities for offences committed by their directors, employees and/or agents and available on the website of COMPANY.

With respect to the performance of the activities under the CONTRACT, CONTRACTOR represents and warrants that it has given and implemented instructions to its directors, employees and/or agents, aimed at preventing the commission or the attempt of any offence under Legislative Decree No. 231 of June 8, 2001 and undertakes vis-à-vis COMPANY to continue effectively implementing such instructions for the entire duration of the CONTRACT. In particular and in accordance with the abovementioned laws and conventions, CONTRACTOR undertakes to abstain (and to cause its directors, employees and/or agents to abstain) from, directly or indirectly, offering, promising, giving, paying or accepting any Public Officials request for a gift, or authorizing anyone to give or pay, directly or indirectly, any sums, other benefits or advantages or anything of value to or for a Public Official or any third party. For the purposes of the CONTRACT, Public Official shall mean:

a) anyone who performs public functions in a legislative judicial or administrative capacity;

b) anyone acting in an official capacity for or on behalf of: (i) a supranational, national, regional or local government, (ii) an agency, department, office or instrumentality of a supranational, national, regional or local government, (iii) a government-owned or government-controlled or government-participated company, (iv) a public international organization and/or (v) a political party, a member of a political party, an official or candidate for political office;

c) anyone in charge of providing a public service; or

d) any other person, individual or entity at the suggestion, request or instruction or for the benefit of any of the persons or entities referred to in paragraphs (a) to (c) above.

With respect to the performance of the activities under the CONTRACT, CONTRACTOR undertakes vis-à-vis COMPANY for the entire duration of the CONTRACT to strictly abide by the principles of the Eni Code of Ethics and to respect human rights as defined in the Eni Guidelines on the Protection and Promotion of Human Rights, available on the website www.eni.com. In particular, CONTRACTOR undertakes to abstain from:

a)	offering commissions, fees and other benefits to directors, employees or agents of COMPANY;

b)	entering into trade agreements with directors, employees or agents of COMPANY which may negatively affect the interests of COMPANY;

c) starting business activities or entering into agreements with THIRD PARTIES in breach of the principles set out in the Eni Code of Ethics which would negatively affect the performance of the CONTRACT;

d) providing directors, employees or agents of COMPANY with non-property benefits also in the form of gifts, means of transportation, hospitality offers which go beyond the limits of the commonly accepted business ethical standard.

The PARTIES agree that any non-compliance, even partial, with the abovementioned representations, warranties and undertakings, which can be reasonably expected to result in adverse consequences for COMPANY, will be considered a material default under the CONTRACT and will entitle COMPANY to unilaterally withdraw, even during its performance, or to terminate the CONTRACT, by delivering notice via registered mail, which shall include a brief summary of the circumstances or of the legal proceedings demonstrating such non-compliance.

In the event of information that could reasonably imply such non-compliance, pending the required verifications or findings COMPANY will have the right to suspend the performance of the CONTRACT by delivering notice via registered mail, which shall include a brief summary of the relevant information. Should the information be obtained from the media, COMPANY shall have the right to exercise such right when the information has been confirmed by an official document of the Judicial Authority and/or otherwise confirmed by the Judicial Authority. The exercise of such rights will be to the sole detriment of CONTRACTOR, which shall bear, in all cases, all additional expenses and costs and shall be liable for and defend, indemnify and hold harmless COMPANY from any THIRD PARTY action arising from or consequential to such non-compliance.

Upon acceptance of the CONTRACT, CONTRACTOR undertakes to:

- comply with the applicable legislation and, in particular, the Anti-Corruption Laws (Italian Penal Code, Legislative Decree no. 231 of 2001 as amended and other applicable regulations, the US Foreign Corrupt Practices Act, the Bribery Act, other regulations of public and commercial law against corruption in force worldwide and international anti-corruption agreements such as the OESD Convention on Combating Bribery of Foreign Public Officials in International Business Transactions and the United Nations Conventions against Corruption) and properly and transparently record in its own books and records all the amounts it will receive under the CONTRACT.

Upon execution of the CONTRACT, COMPANY reserves the right to:

- terminate and/or suspend the CONTRACT and receive compensation for damages, or terminate without cause, as provided by this clause, in case of any breach, even partial, by CONTRACTOR of aforesaid obligations, representations and warranties or in case of violation of the Anti-Corruption Laws;

- carry out audit on CONTRACTOR in the event COMPANY has a reasonable belief that CONTRACTOR may have violated the CONTRACT provisions as aforesaid.

# Alternativa B

(Versione utilizzabile, in alternativa alla precedente, in caso di contratti che prevedono l’esecuzione delle attività all’estero, con controparte straniera)

57.2.	Administrative Responsibility

CONTRACTOR declares to have reviewed and have knowledge of the contents of the document "Model 231", including also the Eni Code of Ethics, drafted by COMPANY in accordance with the legislation in force regarding the administrative liability of legal entities for offences committed by their directors, employees and/or agents and available on the website of COMPANY.

With respect to the performance of the activities under the CONTRACT, CONTRACTOR represents and warrants that it has given and implemented instructions to its directors, employees and/or agents, aimed at preventing any and all conducts in breach of the U.S. Foreign Corrupt Practices Act, the OECD Convention on Combating Bribery of Foreign Public Officials in International Business Transactions, the United Nations Convention against Corruption and any other anti-bribery laws which may be applicable to CONTRACTOR and undertakes vis-à-vis COMPANY to continue effectively implementing such instructions for the entire duration of the CONTRACT. In particular and in accordance with the abovementioned laws and conventions, CONTRACTOR undertakes to abstain (and to cause its directors, employees and/or agents to abstain) from, directly or indirectly, offering, promising, giving, paying or accepting any Public Officials request for a gift, or authorizing anyone to give or pay, directly or indirectly, any sums, other benefits or advantages or anything of value to or for a Public Official or any third party. For the purposes of the CONTRACT, Public Official shall mean:

a) anyone who performs public functions in a legislative judicial or administrative capacity;

b) anyone acting in an official capacity for or on behalf of: (i) a supranational, national, regional or local government, (ii) an agency, department, office or instrumentality of a supranational, national, regional or local government, (iii) a government-owned or government-controlled or government-participated company, (iv) a public international organization and/or (v) a political party, a member of a political party, an official or candidate for political office;

c) anyone in charge of providing a public service; or

d) any other person, individual or entity at the suggestion, request or instruction or for the benefit of any of the persons or entities referred to in paragraphs (a) to (c) above.

With respect to the performance of the activities under the CONTRACT, CONTRACTOR undertakes vis-à-vis COMPANY for the entire duration of the CONTRACT to strictly abide by the principles of the Eni Code of Ethics and to respect human rights as defined in the Eni Guidelines on the Protection and Promotion of Human Rights, available on the website www.eni.com. In particular, CONTRACTOR undertakes to abstain from:

a)	offering commissions, fees and other benefits to directors, employees or agents of COMPANY;

b)	entering into trade agreements with directors, employees or agents of COMPANY which may negatively affect the interests of COMPANY;

c) starting business activities or entering into agreements with THIRD PARTIES in breach of the principles set out in the Eni Code of Ethics which would negatively affect the performance of the CONTRACT;

d) providing directors, employees or agents of COMPANY with non-property benefits also in the form of gifts, means of transportation, hospitality offers which go beyond the limits of the commonly accepted business ethical standard.

The PARTIES agree that any non-compliance, even partial, with the abovementioned representations, warranties and undertakings, which can be reasonably expected to result in adverse consequences for COMPANY, will be considered a material default under the CONTRACT and will entitle COMPANY to unilaterally withdraw, even during its performance, or to terminate the CONTRACT, by delivering notice via registered mail, which shall include a brief summary of the circumstances or of the legal proceedings demonstrating such non-compliance.

In the event of information that could reasonably imply such non-compliance, pending the required verifications or findings COMPANY will have the right to suspend the performance of the CONTRACT by delivering notice via registered mail, which shall include a brief summary of the relevant information. Should the information be obtained from the media, COMPANY shall have the right to exercise such right when the information has been confirmed by an official document of the Judicial Authority and/or otherwise confirmed by the Judicial Authority. The exercise of such rights will be to the sole detriment of CONTRACTOR, which shall bear, in all cases, all additional expenses and costs and shall be liable for and defend, indemnify and hold harmless COMPANY from any THIRD PARTY action arising from or consequential to such non-compliance.

Upon acceptance of the CONTRACT, CONTRACTOR undertakes to:

- comply with the applicable legislation and, in particular, the Anti-Corruption Laws (Italian Penal Code, Legislative Decree no. 231 of 2001 as amended and other applicable regulations, the US Foreign Corrupt Practices Act, the Bribery Act, other regulations of public and commercial law against corruption in force worldwide and international anti-corruption agreements such as the OESD Convention on Combating Bribery of Foreign Public Officials in International Business Transactions and the United Nations Conventions against Corruption) and properly and transparently record in its own books and records all the amounts it will receive under the CONTRACT.

Upon execution of the CONTRACT, COMPANY reserves the right to:

- terminate and/or suspend the CONTRACT and receive compensation for damages, or terminate without cause, as provided by this clause, in case of any breach, even partial, by CONTRACTOR of aforesaid obligations, representations and warranties or in case of violation of the Anti-Corruption Laws;

- carry out audit on CONTRACTOR in the event COMPANY has a reasonable belief that CONTRACTOR may have violated the CONTRACT provisions as aforesaid.

57.3.	Privacy

Either PARTY represents that they have mutually disclosed, with separate documents, information on processing of the other PARTY’s personal data under art. 13 of Legislative Decree no. 196 of 2003.

58.	NOTICES

58.1.	All the notices under the CONTRACT will be in writing and will be deemed validly delivered if they are served personally or sent by registered letter, telegram or fax, to the addresses set out in Art. "Notices" of the Special Conditions.

Said notices will be deemed effective for all purposes as of the date of receipt thereof by the addressee.

58.2.	Each PARTY may change its address subject to at least 15 (fifteen) days’ notice to the other PARTY.

EXHIBIT "A"

ATTACHED TO CONTRACT NO. ......./..

- Upon receipt of the goods under Processing Account supplied by Suppliers and/or COMPANY, CONTRACTOR holding the Account shall:

  - sign the original copy of the documents accompanying the goods received;

  - send the above-mentioned copy to:

Eni S.p.A.

.......................

.......................

.......................

"MAT7" delivery note, issued by COMPANY upon receipt of the copy, shall be used by CONTRACTOR for its notes and to fill in the "Appendix 3" form.

The form shall be filled in at the time of delivery of the WORK resulting from processing.

The goods sent by COMPANY shall be accompanied by the "MAT7" delivery note, whose copy shall be returned to COMPANY signed for receipt.

- The WORK resulting from processing shall be sent to:

........................

........................

........................

- The above-mentioned WORK shall be accompanied by the "Transport Document" (DdT) (or equivalent document), bearing the number of this CONTRACT and Job order..........

- In relation to every delivery made, CONTRACTOR shall fill in the "Appendix 3" form. The form shall be sent to:

Eni S.p.A.

.......................

.......................

.......................

- Each invoice issued by CONTRACTOR shall mention:

  - No. of this CONTRACT;

  - Job order.................;

  - number and date of the "Transport Document" (DdT) (or equivalent document) issued by CONTRACTOR for delivery to COMPANY of the WORK resulting from processing.

- Payment of CONTRACTOR's invoices is conditional upon strict compliance with the above-mentioned instructions.

EXHIBIT "B"

ATTACHED TO CONTRACT NO. ......./..

- The WORK, or any part thereof, assigned to CONTRACTOR, shall be delivered on behalf of COMPANY under Processing Account:

.......................

.......................

.......................

.......................

- At least three copies of the "Transport Document" (DdT) shall accompany the goods to their place of destination.

- The "Transport Documents" (DdT) (or equivalent document) shall be marked "Goods sent for processing on behalf of ENI S.p.A.".

- The invoice, the "Transport Documents" (DdT), and any other document issued by CONTRACTOR shall quote:

Job Order No. ..................

Processing Contract No. ..............

- Payment of CONTRACTOR's invoices is conditional upon strict compliance with the above-mentioned instructions.

EXHIBIT "C"

ATTACHED TO CONTRACT NO. ......./..

DECLARATION OF STORAGE OF WORK ...................

RELATING TO CONTRACT NO. ......./..

BEING PART OF THE PROJECT..............

With reference to the CONTRACT above and the agreements between us we hereby confirm that starting from ../../.... (date of test declaration) the WORK is stored at our facilities (or warehouse...... Street ........ City .........) pending instructions for transport.

- The total value of the WORK stored at our facilities is Euro.........

- We undertake to put in our accounting books the above-mentioned transaction notifying you of its details.

The test declaration issued on ../../.... is therefore deemed valid both for taking receipt of the WORK by You and for paying the share established by the CONTRACT upon occurrence of the event and without prejudice to any limits provided for in the declaration.

As from the above-mentioned date the WORK shall be deemed Your exclusive property, whereas any risk and/or damage caused to the WORK until delivery shall be our responsibility; likewise, we assume all liabilities connected with the correct construction of the WORK under the CONTRACT.

We represent that we waive any lien, for any reason, on the WORK hereunder.

EXHIBIT "D"

ATTACHED TO CONTRACT NO. ......./..

"VARIATIONS TO THE CONTRACT" PROCEDURE